## PIMS
PIMS | Title | Status | Resolution | Security Level | Platform Found | Component Subcomponent | Test Case Number | Issue Severity | Steps to Reproduce | Desciription | Attachments | Activity Comments | Submitted Date | Time lag
PIMS-59363 | Win,21370,WOR2021UPG,FR&PTGL, File Explorer interface will flash garbage when change show/hide under View | CLOSED | Resolved | VENDOR ACCESS Level | FIORANO P MLK , FIORANO TGL | Operating System | 53966.018 | 3-Low | 1. Open File Explorer 2. Click View and change Show/hide option | File Explorer interface will flash garbage when change show/hide under View. Expected Result:. show/hide will follow option change and no any abnormal. Issue isolation: VP on FioranoP TGL VP on Fiorano TGL VP on WOR2021UPG VP on WOR2021FI VNP on 20H2 19042.928 Note: BIOS:0.4.10 OS:Windows October 2021 UPG 21370.1003 OS:Windows October 2021 FI 21364.1001 F/R: 2/2units, 4/4times | File Explorer interface will flash garbage.mp4 4.34 MB 11/May/21 8:39 PM Windows October 2021 Release -EB & WAD issue list 20210610.xlsx 31 kB 14/Jun/21 9:34 PM | Elvis Lee(COMPAL) added a comment - 23/May/21 8:40 PM [0524_SA_Elvis] Issue is VP on UPG_21376.1 and FI_WinOct_21364.1001 and 21380.1001, panel will flash and show garbage when check/uncheck options at View tab in File Explorer. As MSFT Bug #484026 status, MSFT have no plans to address it. It is a transient issue. Elvis Lee(COMPAL) added a comment - 01/Jun/21 2:35 AM [0601_SA_Elvis] Issue is VP on UPG_21385.1002, panel will flash and show garbage when check/uncheck options at View tab in File Explorer. Jian Yang(DELLTEAM) added a comment - 01/Jun/21 2:47 AM MS feedback:Bug was resolved as won't fix,thanks for the bug report. We have no plans to address it. It is a transient issue. Elaine Lu(COMPAL) added a comment - 14/Jun/21 9:33 PM - edited [0615_SA_Elaine]As Dell update, the issue exist in EB list, please refer to the attachment. Windows October 2021 Release -EB & WAD issue list 20210610.xlsx Angie Zhao(COMPAL) added a comment - 14/Jun/21 9:46 PM 20210615_DQA_Angie: base on MS feedback:Bug was resolved as won't fix, no plans to address it. It is a transient issue. (Detail refer Windows October 2021 Release -EB & WAD issue list item 29) | 2021-05-11 20:42 | 71
PIMS-59369 | Win,21364,WOR2021FI,FR&PTGL, File Explorer interface will flash garbage when change show/hide under View | CLOSED | Resolved | VENDOR ACCESS Level | FIORANO P MLK , FIORANO TGL | Operating System | 53966.018 | 3-Low | 1. Open File Explorer 2. Click View and change Show/hide option | File Explorer interface will flash garbage when change show/hide under View. Expected Result:. show/hide will follow option change and no any abnormal. Issue isolation: VP on FioranoP TGL VP on Fiorano TGL VP on WOR2021UPG VP on WOR2021FI VNP on 20H2 19042.928 Note: BIOS:0.4.10 OS:Windows October 2021 UPG 21370.1003 OS:Windows October 2021 FI 21364.1001 F/R: 2/2units, 4/4times | File Explorer interface will flash garbage.mp4 4.34 MB 11/May/21 8:49 PM Windows October 2021 Release -EB & WAD issue list 20210610.xlsx 31 kB 14/Jun/21 9:32 PM | Elvis Lee(COMPAL) added a comment - 23/May/21 8:40 PM [0524_SA_Elvis] Issue is VP on UPG_21376.1 and FI_WinOct_21364.1001 and 21380.1001, panel will flash and show garbage when check/uncheck options at View tab in File Explorer. As MSFT Bug #484026 status, MSFT have no plans to address it. It is a transient issue. Elvis Lee(COMPAL) added a comment - 01/Jun/21 2:35 AM [0601_SA_Elvis] Issue is VP on UPG_21385.1002, panel will flash and show garbage when check/uncheck options at View tab in File Explorer. Jian Yang(DELLTEAM) added a comment - 01/Jun/21 2:46 AM MS feedback:Bug was resolved as won't fix,thanks for the bug report. We have no plans to address it. It is a transient issue. Elaine Lu(COMPAL) added a comment - 14/Jun/21 9:32 PM [0615_SA_Elaine]As Dell update, the issue exist in EB list, please refer to the attachment. Angie Zhao(COMPAL) added a comment - 14/Jun/21 9:47 PM 20210615_DQA_Angie: base on MS feedback:Bug was resolved as won't fix, no plans to address it. It is a transient issue. (Detail refer Windows October 2021 Release -EB & WAD issue list item 29) | 2021-05-11 20:51 | 71
PIMS-58807 | Win,21364,WOR2021FI, FR&PTGL, The taskview will leave over on the desktop when right-click desktop but not selected. | CLOSED | Resolved | VENDOR ACCESS Level | FIORANO P MLK , FIORANO TGL | Operating System | 100563.01 | 3-Low | 1. right-click desktop but not selected,then click the desktop by touchpad. 2. The taskview will leave over on the desktop. | right-click desktop but not selected,then click the desktop by touchpad, The taskview will leave over on the desktop ,Please refer to attachment. Expected Result:. The taskview should be cancelled. Issue isolation: VP on FioranoP TGL VP on Fiorano TGL VP on WOR2021FI VNP on 20H2 19042.928 Note: BIOS:0.4.10 OS:Windows October 2021 FI 21364.1001 Intel Graphics Driver:27.20.100.9510 NV Graphics Driver:27.21.14.6192 F/R: 4/4units, 4/8times | Precision taskview will leave.mp4 3.07 MB 09/May/21 7:54 PM XPS taskview will leave.mp4 3.39 MB 09/May/21 7:54 PM | Elvis Lee(COMPAL) added a comment - 23/May/21 8:41 PM [0524_SA_Elvis] Issue is VP on FI_WinOct_21364.1001, right click on desktop and choose the items with drop-down menu, do not select options then click on desktop directly, the drop-down menu will keep showing rather than be canceled. The function is workale in Expand for more options. Issue is VNP by updrading to OS_21376.1, the UI become to the old version so that cannot duplicate this issue. As MSFT Bug #476169 #476230 ststus, OS_21370 became to old interface, so cannot duplicate the issue. Issue is VNP on the new UI of 21380.1001. Elvis Lee(COMPAL) added a comment - 01/Jun/21 2:36 AM - edited [0601_SA_Elvis] Issue is VNP on FI&UPG_21385.1002, new UI cannot duplicate the issue. Regina Zhu(COMPAL) added a comment - 07/Jun/21 3:55 AM 2021/06/07,QAD_Regina_zhu,this issue VNP on Fiorano&P TGL with BIOS 1.2.0,OS: Windows October 2021 FI 21385.1002,FR:0/2U,0/20T,so close the issue. | 2021-05-09 19:55 | 73
PIMS-58856 | Win,21364,WOR2021UPG,FRPTGL,Microsoft account cannot sign in Feedback Hub always. | CLOSED | Resolved | VENDOR ACCESS Level | FIORANO P MLK | Operating System | 109748.002,step10 | 3-Low | 1.Boot to OS,Start menu->Search->Feedback Hub->Sign in. 2. Try to sign in Feedback by Microsoft account and check result. | Microsoft account cannot sign in Feedback Hub always.Details pls refer to attachment. Expected Result:. Microsoft account can sign in Feedback Hub. Issue isolation: VP on FioranoP TGL VNP on Fiorano TGL VP on WOR2021UPG VNP on 20H2 19042.928(XPS/Precision) Note: BIOS:0.4.10 OS:Windows October 2021 UPG 21364.1001 F/R: 2/2units, 6/6times | Octber_UPG_Precision_feedback Hub cannot sign in.PNG 231 kB 09/May/21 9:15 PM October_UPG_XPS_can sign in ok.PNG 1.51 MB 09/May/21 9:15 PM | 4 older comments Elvis Lee(COMPAL) added a comment - 10/Jun/21 4:30 AM [0610_SA_Elvis] Issue is VP on UPG_21990.1 on DQA side and FI_21990.1 on our side and it will show errer message "Something went wrong" when opening app on UPG_22000.1. As PIMS-64619 (Horizon1517) status, issue also VP on 21990.1 and plans to report MSFT Bug. As MSFT Bug #489259 status, issue also can reproduce on 21990.1 and has already provided logs to MSFT. Elvis Lee(COMPAL) added a comment - 16/Jun/21 5:26 AM [0616_SA_Elvis] Issue is VP on FI_22000.1 and FI_22000.1_hotfix_22000.37, APP can not sign in and will show error message. This is cross-platform issue on PIMS-64619_HORIZON 15/17 and PIMS-59015_ARK/SIF15 TGL. Issue is under tracking on MSFT Bug #489259. Elvis Lee(COMPAL) added a comment - 23/Jun/21 3:02 AM [0623_SA_Elvis] Issue is VP on FI_20H2_UPG_22000.4, APP can not sign in and will show error message "Something went wrong.". Issue is under tracking on MSFT Bug #489259. Elvis Lee(COMPAL) added a comment - 30/Jun/21 2:25 AM [0630_SA_Elvis] Issue is VF on FI_WOR_22000.4 and UPG_22000.4 with Feedback Hub v1.2103.1172.0. F/R: 0/10. Bland yu(COMPAL) added a comment - 01/Jul/21 4:17 AM - edited 2021/7/1,QAD_Bland,this issue VF on October UPG_22000.4(ZPD) with FeedbackHub 1.2103.1172.0,can sign in successfully and if you set password you'll also go through verification page before Welcome! page.So close the issue. | 2021-05-09 21:17 | 73
PIMS-58667 | Win,21364,WOR2021FI,FR&PTGL, The local music and video cannot be played successfully after connecting the Bluetooth headset/speaker. | CLOSED | Resolved | VENDOR ACCESS Level | FIORANO P MLK , FIORANO TGL | Operating System | 54065.023 | 2-Medium | 1. Boot to OS and install the latest driver; 2. Paired a BT headset/speaker with SUT; 3. Play a song or MV, check whether it can play smoothly. | After connecting the Bluetooth headset/speaker: The music cannot be played and will show error, pls refer to attachment; The video can be played, but no sound comes out of the headset/speaker; If play online music first, the headset/speaker can send out sound, If play local music first and then online music, no sound comes out of the headset/speaker. Expected result: The local music and video can play smoothly when the Bluetooth headset/speaker is connected. Issue isolation: VP on FioranoP TGL VP on Fiorano TGL VP on WOR2021FI VNP on WOR2021UPG 21359.1000 VNP on 20H2 19042.928 VNP without BT headset/speaker Note: BIOS:0.4.10 OS:FI 21364.1001 Intel AX201 BT driver:22.40.0.2 Killer 1650 BT driver:22.40.0.2 F/R: 2/2units, 5/5times | can't play MP3 when connected to BT speaker.jpg 1.10 MB 07/May/21 10:48 PM | Elvis Lee(COMPAL) added a comment - 23/May/21 8:42 PM [0524_SA_Elvis] Issue is VP on FI_WinOct_21364.1001 and UPG_WinOct_21376.1, the BT headset has no voice output and it will occur error code "0xc00d36fa" when playing local music . AS MSFT BUG #481615 status, suspect this issue is a duplicate of another bug, which has been fixed in 21384.1.co_release.210513-1440. Issue is VNP on 21380.1001, the local music and video can play normally. Elvis Lee(COMPAL) added a comment - 04/Jun/21 7:18 AM - edited [0604_SA_Elvis] Issue is blocked as MSFT Bug #488479 status, some apps show white underline and can't open on 21385.1002. Issue is VNP on UPG_21990.1, the apps can open and the local music and video can play via BT headset/speaker. Wait for FI cut in OS_21990.1. Maia_Hu(COMPAL) added a comment - 08/Jun/21 3:16 AM 2021/06/08, VF on FI 21990.1, BIOS 1.2.0 | 2021-05-07 22:56 | 75
PIMS-64423 | Win,21380,WOR2021UPG,FR&PTGL, The local music and video cannot be played successfully after connecting the Bluetooth headset/speaker. | CLOSED | Resolved | VENDOR ACCESS Level | FIORANO P MLK , FIORANO TGL | Operating System | 54065.023 | 2-Medium | 1. Boot to OS and install the latest driver; 2. Paired a BT headset/speaker with SUT; 3. Play a song or MV, check whether it can play smoothly. | After connecting the Bluetooth headset/speaker: The music cannot be played and will show error, pls refer to attachment; The video can be played, but no sound comes out of the headset/speaker; If play online music first, the headset/speaker can send out sound; If play local music first and then online music, no sound comes out of the headset/speaker. Expected result: The local music and video can play smoothly when the Bluetooth headset/speaker is connected. Issue isolation: VP on FioranoP TGL VP on Fiorano TGL VNP on 20H2 19042.928 VNP without BT headset/speaker Note: BIOS:1.2.0 OS:UPG 21380.1001 Intel AX201 BT driver:22.40.0.2 Killer 1650 BT driver:22.40.0.2 F/R: 2/2units, 5/5times | can't play mp3 when connect to BT speaker.jpg 1.02 MB 01/Jun/21 5:21 AM | Elvis Lee(COMPAL) added a comment - 04/Jun/21 7:18 AM [0604_SA_Elvis] Issue is blocked as MSFT Bug #488479 status, some apps show white underline and can't open on 21385.1002. Issue is VNP on UPG_21990.1, the apps can open and the local music and video can play via BT headset/speaker. Maia_Hu(COMPAL) added a comment - 08/Jun/21 3:19 AM 2021/06/08, VF on UPG 21990.1, BIOS 1.2.0 | 2021-06-01 06:02 | 50
PIMS-61922 | Win,21364,WOR2021FI,FR&PTGL,PowerDVD show error code=0011 when paly BD disk with PowerDVD 20. | REVIEW | Unresolved | VENDOR ACCESS Level | FIORANO P MLK , FIORANO TGL | Operating System | 59104.023 | 2-Medium | 1、Install PowerDVD 20 and play BD disk. 2、Check if you will find PowerDVD show error code=0011. | Install PowerDVD 20 and play BD disk, you will find PowerDVD show "Playback stopped because your graphics card driver is incompatible. Make sure it meets the minimum requirements. You can find additional information on the CyberLink FAQ web site(code=0011)" Expected Result: PowerDVD paly BD disk normally with PowerDVD 20. Issue isolation: VP on FioranoP TGL VP on Fiorano TGL VP on WOR2021FI VNP on 20H2 19042.928 Note: BIOS:1.0.0 OS:21364.1001 Intel Graphics Driver:27.20.100.9565 NV Graphics Driver:27.21.14.6192 Audio Driver:6.0.9147.1 FR:2/2U 4/4T | External Mail Windows 11_ATS Issue Disposition Please leverage the ATS disposition for same issues filed on your platform(s) and update PIMSPQMVAST.msg 87 kB 28/Jun/21 8:52 PM PowerDVD show error code=0011.jpg 89 kB 20/May/21 1:35 AM | 5 older comments Elvis Lee(COMPAL) added a comment - 23/Jun/21 3:02 AM [0623_SA_Elvis] Issue is VP on FI_22000.2_hotfix_22000.4. Issue is under checking on MSFT Bug #482493. Elaine Lu(COMPAL) added a comment - 28/Jun/21 8:51 PM - edited [0629_SA_Elaine] Issue same as BITS475219 and ATS-P1 approved by OS AQE and leverage on FioranoTGL, please refer to the attachment for detail. Elvis Lee(COMPAL) added a comment - 30/Jun/21 4:11 AM [0630_SA_Elvis] Issue is VP on UPG_22000.4, UPG_22000.51, FI_22000.4 and FI_22000.4_hotfix_22000.51. Issue is under checking on MSFT Bug #482493. Cason huang(COMPAL) added a comment - 02/Jul/21 1:20 AM 2021/7/2, Cason_Huang, issue got ATS P1 approved from October 2021 of VAST system. Elvis Lee(COMPAL) added a comment - 08/Jul/21 1:19 AM [0708_SA_Elvis] As MSFT Bug #482493, the issue will be addressed for the October refresh of Win11. Issue will verify on the October refresh of Win11 when it has been released. | 2021-05-20 01:39 | 62
PIMS-61635 | Win,21376,WOR2021FI, FR&PTGL, Swiping 3-fingers can't switch apps by TP Slide to left/right | CLOSED | Resolved | VENDOR ACCESS Level | FIORANO P MLK , FIORANO TGL | Operating System | 14074.013 step8 | 2-Medium | 1. Boot to OS, open some applications. 2. Swiping 3-Fingers on touchpad from left to right to switch multiple applications. 3. Find it can be same as pressing the "Alt-Tab" which pops up open tasks, but can not select the app we want. Swiping 3-Fingers can't switch apps by TP slide to left/right.-->Issue | Swiping 3-Fingers on touchpad from left to right to switch multiple applications. Find it can be same as pressing the "Alt-Tab" which pops up open tasks, but can not select the app we want. Swiping 3-Fingers can't switch apps by TP slide to left/right. Test Case: 14074.013 Windows-10: The "Precision Touch-pad" Finger Gestures Functionality Test (Notebooks). step 8 Expected Behavior: Swiping 3-Fingers can switch apps by TP slide to left/right normally. Actual Symptom: Swiping 3-Fingers can't switch apps by TP slide to left/right Issue isolation: VP on FioranoP TGL VP on Fiorano TGL VP on WOR2021FI VNP on 20H2 19042.928 Note: BIOS:1.0.0 OS:Windows October 2021 FI 21376.1002 Intel Graphics Driver:27.20.100.9565 NV Graphics Driver:27.21.14.6192 F/R: 2/2units, 6/6times | There is no attachment uploaded | Elvis Lee(COMPAL) added a comment - 24/May/21 3:01 AM [0524_SA_Elvis] Issue is VP on FI_WinOct_21364.1001 and UPG_WinOct_21376.1 and 21380.1001, cannot open task view by swiping 3 fingers. As MSFT Bug #479341 #482481 #477745 #481712 #481714 #482485 #482547 #482541, this is an intentional By Design feature behavior. Elvis Lee(COMPAL) added a comment - 01/Jun/21 2:39 AM [0601_SA_Elvis] Issue is VNP on UPG_21385.1002, the function of swiping 3 fingers can open taskview. Regina Zhu(COMPAL) added a comment - 07/Jun/21 8:04 PM 2021/06/08,QAD_Regina_zhu,Swiping 3-Fingers on touchpad from left to right to switch multiple applications，It's VNP on Fiorano&P TGL with BIOS 1.2.0,OS: Windows October 2021 UPG 21385.10012,FR:0/2U,0/20T,so close the issue. | 2021-05-19 20:20 | 63
PIMS-63349 | Win,21380,WOR2021UPG,FR&PTGL, No response when launching Voice Recorder from Start menu | CLOSED | Resolved | VENDOR ACCESS Level | FIORANO P MLK , FIORANO TGL | Operating System | 35853.015 | 2-Medium | 1,Click App List and launch Voice Recorder 2. Find can't launch Voice Recorder | No response when launching Voice Recorder from Start menu,Please refer to attachment, Expected Result:. launching Voice Recorder is normal Issue isolation: VP on FioranoP TGL VP on Fiorano TGL VP on WOR2021UPG VNP on 20H2 19042.928 Note: BIOS:1.0.0 OS:Windows October 2021 UPG 21380.1001 Intel Graphics Driver:27.20.100.9565 NV Graphics Driver:27.21.14.6192 Audio Driver:6.0.9147.1 F/R: 2/2units | No response when launching Voice Recorder .mp4 1.11 MB 25/May/21 8:11 PM | Elvis Lee(COMPAL) added a comment - 01/Jun/21 2:39 AM [0601_SA_Elvis] Issue is VP on UPG_21385.1002, the voice recorder has no response when clicking it from start menu. As MSFT Bug #482437 status, it is a known issue to MSFT and is still working on it. Elvis Lee(COMPAL) added a comment - 04/Jun/21 7:22 AM [0604_SA_Elvis] Issue is VNP on UPG_21990.1, the voice recorder can open and can record normally. Regina Zhu(COMPAL) added a comment - 10/Jun/21 3:21 AM 2021/06/10,QAD_Regina_zhu,this issue VP on Fiorano&P TGL with BIOS 1.2.0, OS: Windows October 2021 UPG_21990.1,FR:2/2U,4/4T，So turn this issue to analyse. Elvis Lee(COMPAL) added a comment - 10/Jun/21 4:54 AM [0610_SA_Elvis] Issue is VP on UPG_From_20H2_to_Cobalt_21990.1 and 22000.1 but VNP on UPG_From_Cobalt_to_Cobalt. As MSFT Bug#490093 status, issue is VP on UPG_21990 and UPG 21996, app can open on FI_21990 but will show message "Voice Recorder needs an update,but we're unable to apply the update right now". As MSFT Bug#485181 status, MSFT feedback it should be fix on 22000+. Elvis Lee(COMPAL) added a comment - 16/Jun/21 4:10 AM - edited [0616_SA_Elvis] Issue is VP on FI_20H2_UPG_22000.1 and FI_20H2_UPG_22000.1_hotfix_22000.37 but VNP on FI_22000.1 and FI_22000.1_hotfix_22000.37. As MSFT Bug #482366 #485181 #482493 status, issue still can reproduce on 22000 and MSFT does not reply yet. Related PIMS-59559 - SIF G15. Keep tracking MSFT Bug status. Elvis Lee(COMPAL) added a comment - 23/Jun/21 3:02 AM - edited [0623_SA_Elvis] Issue is VF on FI_20H2_UPG_22000.1, 22000.2 and 22000.4. Voice Recorder can be open after updating by MSFT Store and the version of Voice Recorder is v.10.2103.28.0. Regina Zhu(COMPAL) added a comment - 24/Jun/21 8:11 PM 2021/06/25,QAD_Regina_zhu,this issue VNP on Fiorano&P TGL with BIOS 1.3.1,OS: Windows October 2021 UPG 22000.1,FR:0/2U,0/10T, By updating Voice Recorder is v.10.2103.28.0, so close the issue | 2021-05-25 20:12 | 57
PIMS-64235 | Win,21385,WOR2021UPG,FR&PTGL,can't open "Windows Security settings". | CLOSED | Resolved | VENDOR ACCESS Level | FIORANO P MLK , FIORANO TGL | Operating System | 102736.009 | 2-Medium | 1.In search window,input "Windows Security Settings"-> click on "Open Windows Security" and check. | SUT can't open "Windows Security settings". Expected Result:. SUT open "Settings" item and view without any issue. Issue isolation: VP on FioranoP TGL VP on Fiorano TGL VP on WOR2021UPG VNP on 20H2 19042.985 Note: BIOS:1.0.0 OS:Windows October 2021 UPG 21385.1002 F/R: 3/3units, 6/6times. | screenshot-1.png 51 kB 01/Jun/21 12:04 AM | Sk_Wang added a comment - 01/Jun/21 12:04 AM Elvis Lee(COMPAL) added a comment - 04/Jun/21 7:20 AM [0604_SA_Elvis] Issue is VP on UPG_21385.1002 but VNP on UPG_21990.1, Windows Security settings can open on UPG_21990.1. Bland yu(COMPAL) added a comment - 08/Jun/21 4:33 AM 2021/6/8,QAD_Bland,this issue VF on October UPG_21990.1,no issue when openning "Windows Security settings",so close the issue. | 2021-05-31 20:54 | 51
PIMS-66518 | [EVT_FR&PADL_RSV]Hynix RAM damaged at 2 degrees environment temperature | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL | Hardware | 108601 Power cycling test | 1-High | Follow REL 1078 A14 power cycling test item to reproduce. | Hynix 16G RAM damaged at 2 degrees environment temperature when operated power cycling validation item , SUT can't boot up and LED show 2A3W. RAM DPN : VNY72 , CPN: PK05500021L F/R: 2/2pcs | RE External Mail RE Fiorano ADL-P Hynix 16GB DDR5 SO-DIMM damaged on EVT board analysis.msg 224 kB 01/Jul/21 3:57 AM | Bill Wu(COMPAL) added a comment - 01/Jul/21 3:57 AM Hynix feedback What you have is ES sample. The ES sample is provided for function test, not reliability test. For reliability test, please use CS sample. It will turn wait till CS sample. 07/01 update by Bill | 2021-06-16 21:04 | 35
PIMS-65137 | [EVT_FR&PADL] SUT can't boot with Micron memory and LED show 2A3W. | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | System Board | 14562.013 | 1-High | 1.Boot SUT with Micron memory. | SUT can't boot with Micron memory and LED show 2A3W. But SUT boot normally with Hynix memory. Expected result: SUT boot normally with Micron memory. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VP on Micron memory VNP on Hynix memory Note: BIOS:0.0.0 OS:October2021_21380.1001 F/R: 2/2units, 4/4times. | DELL RMA 42273353-100 Final report.pdf 159 kB 03/Jul/21 7:52 PM | Bill Wu(COMPAL) added a comment - 22/Jun/21 10:24 AM - edited 1. Ship 7pcs 8GB + 2pcs 32GB damaged DDR5 module to Micron analyze , FA report offer end of WW28 2. Found out there will occur inrush current over 2.5A(SPEC is max 2A in each DIMM)with Micron DDR5 when AC plug in , it changed to load switch and then found out the inrush current rest of around 0.32A. 3. Reworked all of PCBA where located in LKE , after monitor 2 week that there is no any DDR5 damage issue occurred. 4. Load switch solution will implement on DVT1. 06/22 update by Bill Bill Wu(COMPAL) added a comment - 03/Jul/21 7:51 PM - edited 1. FA as attachment : These modules function test was passed but failed NO-BOOT on the system. Checking SPD data, the bit data for Byte 2, 3, 5, 200, 203 not matching to our datasheet. Byte 2, 3, 5 were wrong which cause the module locked up on system. 2. Ship all damaged DDR5 module to Micron rewrite and check status. 07/04 update by Bill | 2021-06-05 03:34 | 46
PIMS-64550 | [EVT_FR&PADL] TBT port can't light TBT monitor | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | CPU | 14562.013 | 1-High | 1. Boot to OS, plug TBT monitor to TBT port, check monitor light or not | TBT port can't light TBT monitor. Device Manager can detect monitor but can't light it. Expected Result: TBT port should can light TBT monitor. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS: 0.0.0 OS: October2021_21380.1001 | 635566_ADL_M_P_TBTDisplayTunnelingIssue_SA_WW10_2021.pdf 120 kB 06/Jun/21 10:13 PM | Nelson Yang(COMPAL) added a comment - 06/Jun/21 10:11 PM it's Intel CPU problem as the attached file. EE will follow up to track issue with Intel Bill Wu(COMPAL) added a comment - 21/Jun/21 9:10 PM - edited 1. Intel planned in future ADL QS to fix. 2. It will turn wait and verify on QS CPU. 06/22 update by Bill | 2021-06-02 20:09 | 49
PIMS-72517 | [EVT_FR&PADL_D] GPU State show "on" several times when SUT idle 10 min after WB/CB. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | Driver | 14707.031 | 2-Medium | 1、Open GPUmon after SUT resume from WB/CB. 2、Let SUT idle 10min, check if GPU State show "on" several times | Open GPUmon after SUT resume from WB/CB, let SUT idle 10min, you will find GPU State show "on" several times Issue isolation: VP: Fiorano ADL VP: FioranoP ADL VP: GN20-P0/GN20-P1/QN20-P3 ** Note: BIOS:0.0.6 OS:October 2021_22000.4 Intel Graphics Driver:30.0.100.9654 NV Graphics Driver:27.21.14.7135 Audio Driver:6.0.9196.1 F/R:3/3u, 6/6t | GPU State.mp4 6.45 MB 20/Jul/21 8:25 PM | There are no comments yet on this issue. | 2021-07-20 20:31 | 1
PIMS-72221 | [EVT_FR&PADL]MEBx version still show "16.0.0.0001" after ME disable. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 14355.022 | 2-Medium | 1. ME disable via FactoryTestConfiguration; 2. Run MEInfo, check MEBx version. | After ME disable, run MEInfo, found MEBx version show "16.0.0.0001". Expected result: After ME disable, MEBx version should show "0.0.0.0" Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VP: ME disable via Service Menu Note: BIOS:0.0.6 OS:October2021_22000.4 Intel AX211 WLAN driver:22.55.0.1 ME Driver:2121.16.0.2299 F/R: 2/2units, 5/5times | MEBx version.JPG 350 kB 19/Jul/21 8:45 PM | There are no comments yet on this issue. | 2021-07-19 20:49 | 2
PIMS-72197 | [EVT_FRPADL]AMT_Run "MEManuf.efi" failed | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO P MLK2 | BIOS | 14189.02 | 2-Medium | 1. Boot SUT to EFI key; 2. Run "MEManuf.efi". | Run "MEManuf.efi" failed; Run "MEManuf.efi -S0" failed; Run "MEManuf.efi -verbose" failed; Run "MEManuf.efi -nextreboot" pass. Expected result: No error appeared after run "MEManuf.efi" Issue isolation: VP: EFI/WinPE/Windows environment. ME disable can not duplicate Note: BIOS:0.0.6 OS:October2021_22000.4 Intel AX211 WLAN driver:22.65.0.1 ME Driver:2121.16.0.2299 ME FW:16.0.0.1358 F/R: 2/2units, 5/5times | error.log 0.1 kB 19/Jul/21 8:11 PM | There are no comments yet on this issue. | 2021-07-19 20:38 | 2
PIMS-71856 | [EVT_FRPADL]AMT_Can't enumerate the BIOS attributes remotely via DVED. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO P MLK2 | BIOS | 14368.018 | 2-Medium | 1. Perform TLS provisioning. 2. Use DVED remote console to connect SUT. 3. Enumerate the BIOS attributes. | DVED can't enumerate BIOS attributes, it will shows "Warning: Client returned no BIOS attributes. Contact your administrator." Expected result: Enumerate the BIOS attributes successfully. Note: BIOS:0.0.5 OS:October2021_22000.4 Intel AX211 WLAN driver:22.65.0.1 ME Driver:2121.16.0.2299 ME FW:16.0.0.1358 DVED_X43_v1.0.0¦ F/R: 2/2units, 5/5times | warning.jpg 373 kB 17/Jul/21 1:29 AM | There are no comments yet on this issue. | 2021-07-17 02:22 | 4
PIMS-71802 | [EVT_FR&PADL]SUT show blackscreen conntected with monitor after resume from MS. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | Video | 54004.027 | 2-Medium | 1、Connect Monitor to SUT with HDMI/DP/Type-c. 2、Put SUT to MS Mode by lid close/power button. 3、Wait for 15 seconds and wake up SUT from MS Mode. Check if SUT show blackscreen. | Connect Monitor to SUT with HDMI/DP/Type-c, Put SUT to MS Mode by lid close/power button. Wait for 15 seconds and wake up SUT from MS Mode. You will find SUT show blackscreen. Issue isolation: VP: Fiorano ADL VP: FioranoP ADL ** Note: BIOS:0.0.5 OS:October 2021_22000.4 Intel Graphics Driver:30.0.100.9654 NV Graphics Driver:27.21.14.7130 Audio Driver:6.0.9196.1 F/R:3/3u, 6/30t | SUT show blackscreen.MP4 7.85 MB 16/Jul/21 8:17 PM | Wendy Liang(COMPAL) added a comment - 21/Jul/21 4:16 AM [0721_SA_Wendy] New issue, still CND in LKE. Keep reproducing. | 2021-07-16 21:10 | 5
PIMS-71558 | [EVT_FR&P ADL] Master System Password can't clear admin and system password by CTRL-Enter Key. | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | Embedded Solutions | 13579.028 | 2-Medium | 1,Clear service Tag with Mfg Tool 2,Set service Tag "BBBBBBB" and save change in BIOS Setup. 3,Set Admin and System password ang keep your mind what you set. 4,Shut down and reboot,type in corresponding Master System Password when system password prompt.Then hit CTRL-Enter Key. | Admin and System password can't be cleared by Master System Password via CTRL-Enter Key. Expected result: Admin and System password can be cleared by Master System Password via CTRL-Enter Key. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.5 OS: October2021_22000.4 F/R: 2/2u,6/6T. | clear fail.jpg 872 kB 15/Jul/21 9:57 PM Master Password_EC Fuse.jpg 208 kB 20/Jul/21 9:31 PM | Lanny Lan(COMPAL) added a comment - 20/Jul/21 6:46 AM - edited Refer to PIMS-34122, this issue need Auto Fuse EC FW to verify. Please refer to screen shot which captured from EC security v1.0 document. Kate Tsao(COMPAL) added a comment - 20/Jul/21 10:44 PM Turn status to Wait to wait Fuse EC. Lanny Lan(COMPAL) added a comment - 21/Jul/21 1:16 AM Transfer to EC pal because Master Password feature is related to Fused EC FW. | 2021-07-15 21:59 | 6
PIMS-71505 | [EVT_FR&PADL] Run Passmark Performance 3D Graphic Test will show warning. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | Operating System | 109401 | 2-Medium | 1. Install Passmark performance tool. 2. On the Tool UI, click on Tests tab and select "3D Graphics" > run All 3. Check if it will show warning:Nothing will be rendered | Install Passmark performance tool. On the Tool UI, click on Tests tab and select "3D Graphics" > run All,find it will show warning:Nothing will be rendered Issue isolation: VP: Fiorano ADL VP: FioranoP ADL VP: GN20-P0/GN20-P1/QN20-P3 ** Note: BIOS:0.0.5 OS:October 2021_22000.4 Intel Graphics Driver:30.0.100.9654 NV Graphics Driver:27.21.14.7130 Audio Driver:6.0.9196.1 F/R:3/3u, 6/6t | Run Passmark Performance 3D Graphic Test will show warning.jpg 232 kB 15/Jul/21 8:18 PM | Wendy Liang(COMPAL) added a comment - 19/Jul/21 12:09 AM - edited [0719_SA_Wendy] Same issue on Horizon MLK (PIMS-67862) and Axion/SIF (PIMS-69573). DX9 will be removed in ADL graphic driver, D3D9 will be supported with the translation layer called 9on12 which is OS translation layer. NV had submitted their own MSbug#503602 for debugging from OS view. Suspect same rootcause as PIMS-71494, tracking OSbug#512398 which is filed by Horizon. Transfer the subsystem to OS. | 2021-07-15 20:21 | 6
PIMS-71494 | [EVT_FR&PADL] NVDIA Control panel can't show preview image. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | Operating System | 15295 | 2-Medium | 1、Open NVDIA Control panel\3D Settings\Adjust image settings with preview . 2、Check if Image of Preview in NVDIA Control panel show white background. | Open NVDIA Control panel\3D Settings\Adjust image settings with preview ,Find The Image of Preview in NVDIA Control panel show white background. Issue isolation: VP: Fiorano ADL VP: FioranoP ADL VP: GN20-P0/GN20-P1/QN20-P3 ** Note: BIOS:0.0.5 OS:October 2021_22000.4 Intel Graphics Driver:30.0.100.9654 NV Graphics Driver:27.21.14.7130 Audio Driver:6.0.9196.1 F/R:3/3u, 6/6t | NVDIA Control panel can't show preview image.jpg 160 kB 15/Jul/21 8:09 PM | Wendy Liang(COMPAL) added a comment - 15/Jul/21 10:14 PM - edited [0716_SA_Wendy] DX9 will be removed in ADL graphic driver, D3D9 will be supported with the translation layer called 9on12 which is OS translation layer. NV had submitted their own MSbug#503602 for debugging from OS view. Same issue as PIMS-67589, tracking OSbug#512407 which is filed by Horizon. Transfer the subsystem to OS. | 2021-07-15 20:14 | 6
PIMS-71430 | [EVT_FR&PADL]4K Video will lag on SUT . | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | Video | 63336.025 | 2-Medium | 1、Play 4K video with Moive&TV on SUT, check if 4K Video will lag. | Play 4K video with Moive&TV on SUT, you will find 4K Video will lag. Expected Result: 4K Video shoudn't lag on SUT . Issue isolation: VP: Fiorano ADL VP: FioranoP ADL ** Note: BIOS:0.0.5 OS:October 2021_22000.4 Intel Graphics Driver:30.0.100.9608 NV Graphics Driver:27.21.14.7076 Audio Driver: 6.0.9196.1 F/R:2/2u, 6/6t | 4K video lag.mp4 3.03 MB 15/Jul/21 5:36 AM | Wendy Liang(COMPAL) added a comment - 16/Jul/21 5:49 AM [0716_SA_Wendy] Different result on 2 pcd with same SSD. Under investigating. Wendy Liang(COMPAL) added a comment - 21/Jul/21 3:08 AM [0721_SA_Wendy] Issue can be seen only when CPU is in low speed 0.4Ghz. For CPU low speed, which has been fixed by EC update in BIOS 0.0.6. | 2021-07-15 05:41 | 6
PIMS-71052 | [EVT_FR&P ADL]Wake on Lan via salomon dock fail | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 57485 | 2-Medium | 1. SUT can't Wake on Lan from S4/S5 by WOL32.exe via salomon dock | Description: SUT can't Wake on Lan from S4/S5 by WOL32.exe via salomon dock Expected result: SUT can Wake on Lan from S4/S5 by WOL32.exe via salomon dock Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VP on WD19 VP on WD19TB VP on WD19DC Note: BIOS:0.0.5 OS: 22000.65 F/R: 2/2units. WD19 FW:A04 Realtek USB Gbe:10.39.518.2020 | There is no attachment uploaded | There are no comments yet on this issue. | 2021-07-14 03:07 | 7
PIMS-70931 | [EVT_FRP ADL] Dell logo display incorrectly during CB/S4. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO P MLK2 | BIOS | 13582.015 | 2-Medium | 1.Place the system into S4, wait 30 seconds, and then wake. 2. resume from S4 ,the system show garbage -->Issue. | Description: Dell logo display incorrectly during CB/S4. Expected result: Dell logo display correctly during CB/S4. Issue isolation: VP on FioranoP ADL VP on UHD FHD PN:451ASD31L51 #2 SN:7108156000033 PN: 451ASD31L51 #1 SN:7108156000034 Note: BIOS:0.0.5 F/R: 2/10units, | VID_20210715_095401[1].mp4 12.16 MB 14/Jul/21 9:00 PM | Wendy Liang(COMPAL) added a comment - 21/Jul/21 2:33 AM [0721_SA_Wendy] Issue VP without any driver installed. Transfer issue to BIOS team for further tracking. | 2021-07-13 22:42 | 8
PIMS-70909 | [EVT_FR&PADL] Device Manger show "Waves Audio Effects Component" YB after update new driver and then roll back to old driver. | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | Audio | 55900.011 | 2-Medium | 1. Install old Audio Driver(6.0.9159.1) successfully. 2.Update new Audio Driver(6.0.9196.1) in Device Manger and restart SUT. 3.Check if Device Manger show "Waves Audio Effects Component" YB. 4. Roll back to old driver. 5. Check if Device Manger still show"Waves Audio Effects Component" YB. | Install old Audio Driver(6.0.9159.1) successfully. Update new Audio Driver(6.0.9196.1) in Device Manger and restart SUT, you will find Device Manger show"Waves Audio Effects Component" YB. Then Roll back to old driver, Device Manger still show"Waves Audio Effects Component" YB. Expected Result: Device Manger shouldn't show YB after update new driver and then roll back old driver. Issue isolation: VP: Fiorano ADL VP: FioranoP ADL *Note:*BIOS:0.0.5 OS:October 2021_22000.4 Intel Graphics Driver:30.0.100.9608 NV Graphics Driver:27.21.14.7076 Audio Driver: 6.0.9196.1 F/R:2/2u, 4/4t | Waves Audio Effects Component YB.jpg 223 kB 13/Jul/21 9:46 PM | Jamiekk Chen(COMPAL) added a comment - 15/Jul/21 3:44 AM [0715_SA_Jamie] X00 driver package uses MA10 with Waves10De.inf and X01 driver package uses MA11 with Waves11De.inf. Waves10De.inf cannot be found by the system in the X01 driver package while updating the whole driver from device manager; hence the YB occurs. Updating with single inf would not cause YB. YB would not occur when updating the whole driver package that both uses MA11. Turns issue to wait until audio driver turns X02. | 2021-07-13 21:46 | 8
PIMS-70858 | [EVT_FR&P ADL] The system & NVMe password prompt angin for the next boot. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 13582.015 | 2-Medium | 1.Set a “system password” . 2. Shutdown then remove battry and memory. 3.Power on, Boot to OS, The System password prompt angin-->Issue. | Description: Create an error/failure event (examples: remove memory, low battery,fan error...).The system & NVMe password prompt angin for the next boot. Expected result: The system password prompts only once Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.5 F/R: 2/2units | VID_20210712_140436.mp4 72.74 MB 13/Jul/21 7:45 PM | There are no comments yet on this issue. | 2021-07-13 19:40 | 8
PIMS-70633 | [EVT_FR&P ADL] Permanently disabled device is still running under the e-Diags tests | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 13633.029 | 2-Medium | 1. Boot to OS run MfgMode64W.exe +dfmm, PlatCfg2W64.exe -set PDF_ Microphone =Disabled ,PlatCfg2W64.exe -set PDF_ Audio=Disabled to permanently disabled Audio port, MfgMode64W.exe camm. 2. Reboot to boot menu then run ePSA/Diags tests , found Audio is still running-->problem | Boot to OS run PlatCfg2W64.exe -set PDF_Audio=Disabled to permanently disabled Audio port, Reboot to boot menu then run ePSA/Diags tests , found Audio is still running Expected result: Boot to the Boot Menu. Select/run the thorough ePSA/Diags tests ensuring no issues - also ensure permanently disabled devices/ports are not run. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.5 OS: October2021_22000.4 F/R: 2/2u,2/2T. | 4.JPG 33 kB 13/Jul/21 12:58 AM | There are no comments yet on this issue. | 2021-07-13 01:21 | 8
PIMS-70596 | [EVT_FR&P ADL] Admin/system/NVMe password(all) can be changed with secure value passwords set. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 100718.015 | 2-Medium | 1. In BIOS Setup, set simple, different 4 character Admin, System, and HDD Passwords(all) (examples: “dell”, “1234”, “ABCD”, “$$$”…). Record values. 2.Change the Admin, System, and HDD Passwords(all) to secure values (examples: “Pa$$word1”, “1G Monk!”, “Mike8@Dell.com”…). Record values. 3. Attempt to change Admin, System, and HDD Passwords(all) using the old simple value passwords (from couple steps previous - examples: “dell”, “1234”, “ABCD”, “$$$”…) ensuring passwords are not changed. | Admin/system/NVMe password(all) can be changed with secure value passwords set. Expected result: Passwords not changed with secure value passwords set. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.5 F/R: 2/2units | There is no attachment uploaded | There are no comments yet on this issue. | 2021-07-12 21:09 | 9
PIMS-70361 | [EVT_FRP ADL] Intel AX211 WiFi Driver shows YB in Device Manager after installed. (via DUP install) | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO P MLK2 | Driver | 13896 | 2-Medium | 1.Directly install Intel AX211 WiFi Driver(DUP) and check DM. | Intel AX211 WiFi Driver shows YB in Device Manager after installed.(via DUP install & BT driver exist:22.40.0.2 or 22.60.0.3 cover install) Details pls refer to attachment. Expected result: No issue when install Intel AX211 WiFi Driver. Issue isolation: VP on FioranoP ADL CNV on Fiorano ADL(tracking PIMS-69087) Note: BIOS:0.0.4 F/R: 5/5units Intel AX211 WiFi Driver:22.65.0.1 | WLAN Driver show YB.PNG 244 kB 11/Jul/21 8:15 PM | Elvis Lee(COMPAL) added a comment - 13/Jul/21 5:55 AM [0713_SA_Elvis] Issue is VP when system has installed AX211 Wi-Fi driver v22.65 with BT drvier v22.40. Confirmed with vendor that this is driver compatibility issue of AX211 Wi-Fi v22.65 needs to correspond with BT v22.60. Issue will be tracking on the next released driver. Elaine Lu(COMPAL) added a comment - 20/Jul/21 9:49 PM [0721_SA_Elaine] Keep tracking next Intel BKC driver release new version. | 2021-07-11 20:16 | 10
PIMS-70356 | [EVT_FR&P ADL] SUT shows "Error 238:The host CPU does not have write access…FPT Operation Failed." when flash BIOS 0.0.5. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 13435.041 | 2-Medium | 1.Flash BIOS and check. | SUT shows "Error 238:The host CPU does not have write access…FPT Operation Failed." when flash BIOS 0.0.5. MB PN: 451ASD31L60#6 451ASD31L51#2 451ASB31L56#2 Expected result: No issue when flash BIOS. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.5 F/R: 3/10units | Error 238.png 1.31 MB 11/Jul/21 8:03 PM | There are no comments yet on this issue. | 2021-07-11 20:04 | 10
PIMS-70104 | [EVT_FR&P ADL] CPU frequency can't keep at processor base core frequency when Intel SpeedStep is disabled. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 14567.025 | 2-Medium | 1. Install the latest driver and BIOS; 2, Boot to BIOS.ensure Intel SpeedStep default is Enable and set to Disable.Set Performance\ Intel TurboBoost to disable. Set Power \Intel Speed Shift Technology to disable.Save and exit. 3. Boot to the OS. Install latest TAT Tool. Open Task manger and Resource Monitor; 4. Run TAT, select Monitor All , click start Monitor. 5. Observe CPU frequency on TAT, find the CPU frequency have changes.can't keep at the Processor Base Core Frequency. | When Intel SpeedStep is disabled, Intel TurboBoost to disable, Intel Speed Shift Technology disable, let the system sit idle or 50% CPU Power workload , observe the frequency of all cores in TAT or Task manager, it is found that CPU frequency cannot be keep at processor base core frequency (spec is 0.8GHz) Details pls refer to attachment Expected result: All cores speed keep un-change and are running at the Processor Base Core Frequency Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VP on DC mode CNV on AC mode(tracking PIMS-69155) Note: BIOS:0.0.4 OS: October2021_22000.4 TAT version:1.0.1002 F/R: 2/2units.2/2T | CPU frequency can't keep.png 1020 kB 09/Jul/21 10:53 PM CPU frequency cannot be keep at processor base core frequency.mp4 1.62 MB 09/Jul/21 10:53 PM | Deckard Chen(COMPAL) added a comment - 21/Jul/21 12:56 AM - edited HI Regina Zhu(COMPAL)Bios 0.0.6 fix this issue, Please depending on the TAT tool check CPU frequency, not use Task manager check | 2021-07-09 22:53 | 12
PIMS-70099 | [EVT_FR&P ADL] Max core(1/2/4/6 core) Turbo Frequency can't meet spec. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 14586.022 | 2-Medium | 1,Boot to BIOS and set Performance\ Intel TurboBoost to Enable. Save. 2, Set power option = Best Performance and Repeat Waiting DTS<50C Step. 3, Run Cinebench\ CPU(single core) or Apply 100% CPU utilization workload with(2/4/6 core) in TAT, Observe the frequency and find Turbo Frequency can't meet spec | Max Core Turbo Frequency can't meet spec when run Cinebench or TAT. The CPU frequency is about below 1GHz. Max Core Turbo Frequency Spec: Max Core Turbo Frequency [GHz] (1-Core):4 Max Core Turbo Frequency [GHz] (2-Core):4 Max Core Turbo Frequency [GHz] (4-Core):3.8 Max Core Turbo Frequency [GHz] (6-Core):3.6 Expected result: All Max Core Turbo Frequency can meet spec. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VP on 1/2/4/6 core VP on DC mode CNV on AC mode(tracking PIMS-69155) Note: BIOS:0.0.5 OS: October2021_22000.4 Cinebench:20.0.6,0 TAT version:1.0.1002 F/R: 2/2units.2/2T | There is no attachment uploaded | There are no comments yet on this issue. | 2021-07-09 22:41 | 12
PIMS-70096 | [EVT_FR&P ADL] Service Tag will be lost after power on with DC mode | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | System Board | 13564 | 2-Medium | 1,flash bin.bios 0.0.5 and set service tag. 2,Power off SUT form start menu in DC mode. 3,power on SUT via power button in DC mode,find Sut Service Tag will be lost. | Service Tag will be lost after power on with DC mode. Fail MB: 451ASD31L51 #6 451ASB31L56 #2 451ASB31L60 ＃3 Expected result: Service Tag not lost after power on with DC mode Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VP on DC mode VNP on AC mode Note: BIOS:0.0.5 OS: October2021_22000.4 F/R: 3/8u,3/40T. | There is no attachment uploaded | There are no comments yet on this issue. | 2021-07-09 22:23 | 12
PIMS-70002 | [EVT_FR&P ADL] SUT shows "Error 181:Hardware timeout occurred in SPI device" when first time flash BIOS 0.0.5. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 13435.041 | 2-Medium | 1.Flash BIOS and check. | SUT shows "Error 181:Hardware timeout occurred in SPI device" when first time flash BIOS 0.0.5. MB PN: 451ASD31L51#4 451ASD31L51#6 451ASB31L56#1 451ASD31L09#1 Expected result: No issue when flash BIOS. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.5/0.0.3 F/R: 4/10units | Error 181.jpg 204 kB 09/Jul/21 12:51 AM | There are no comments yet on this issue. | 2021-07-09 00:53 | 12
PIMS-69970 | [EVT_FR&PADL]AMT_IPETs_ME_PM_45 test run fail. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 14509.014 | 2-Medium | 1.Install iPETs Console in server and PETs Agent in SUT; 2.Open iPETs Console and add SUT info from server; 3.Select test XML file with "Compliance_ME_Power_Gating.xml" from iPETs Console; 4.Follow step run ME_PM_45. | Run ME_Power_Gating.xml-->ME_PM_45 will failed at "Check if Last Boot was from Hibernate". Please refer to attached picture. Expected result: Same results as mentioned in compliance guide. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.4 OS:October2021_22000.4 Intel AX211 WLAN driver:22.55.0.1 ME Driver:2113.16.0.7363 iPETS tool:11.8.0.0¦ F/R: 2/2units, 5/5times | ME_PM_45.jpg 446 kB 08/Jul/21 9:12 PM | Wayne Lu (Compal) added a comment - 13/Jul/21 1:00 AM Hi Maia_Hu(COMPAL) May I know what is the sku of your M/B? Thanks. Could you double confirm your M/B can enter Hibernate mode by manual? | 2021-07-08 21:35 | 13
PIMS-69953 | [EVT_FR&PADL] OOBE flash or show garbage when login in a new user. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | Video | 34955.01 | 2-Medium | 1.Windows Settings->Accounts->Family &other users->add a new user 2.Login in the new user. 3.Check if OOBE show garbage. | Add and login in a new user, you will find OOBE flash or show garbage. Expected Result: OOBE shouldn't flash or show garbage. Issue isolation: VP: Fiorano ADL VP: FioranoP ADL VP: UHD+/OLED/FHD+ ** Note: B BIOS:0.0.4 OS:October 2021_22000.4 Intel Graphics Driver:30.0.100.9608 NV Graphics Driver:27.21.14.7076 Audio Driver:6.0.9159.1 F/R:3/4u, 13/20t | OOBE flash.mp4 13.47 MB 08/Jul/21 7:51 PM OOBE show garbage.mp4 8.15 MB 08/Jul/21 7:51 PM | Wendy Liang(COMPAL) added a comment - 16/Jul/21 5:48 AM [0716_SA_Wendy] Issue VP with pureOS + GFX_9654 on Fiorano ADL, VNP on Tributo ADL/ Protofino ADL with same OS/Driver. Issue VP with w28 bugcheck_9802. Wendy Liang(COMPAL) added a comment - 21/Jul/21 3:08 AM [0721_SA_Wendy] Issue can be seen only when CPU is in low speed 0.4Ghz. For CPU low speed, which has been fixed by EC update in BIOS 0.0.6. | 2021-07-08 19:55 | 13
PIMS-69730 | [EVT_FRADL_D] NV Driver show YB on Device Manger after restart SUT(single unit). | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | System Board | 51013.036 | 2-Medium | 1、Install NV Graphics Driver and restart SUT, Check if NV Graphics Driver show YB on Device Manger. | Install NV Graphics Driver and restart SUT, you will find NV Graphics Driver show YB on Device Manger. ** NV Graphics Driver still show YB on Device Manger with another SSD. ** 451ASB31L56#1 ** Expected result: NV Driver shouldn't show YB on Device Manger after restart SUT ** Issue isolation: VNP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.4 OS:October 2021_22000.4 Intel Graphics Driver:30.0.100.9608 NV Graphics Driver:27.21.14.7076 Audio Driver:6.0.9159.1 F/R: 1/3units | NV YB.MP4.mp4 12.74 MB 07/Jul/21 7:55 PM | There are no comments yet on this issue. | 2021-07-07 19:59 | 14
PIMS-69330 | [EVT_FR&P ADL] Dell logo will flash once during boot. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 13435.041 | 2-Medium | 1. Boot and check Dell logo. | Dell logo will flash once during boot. Expected result: Dell logo should no any abnormal during boot. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.4 F/R: 2/2units, 4/4times. | Dell logo will flash once.mp4 6.66 MB 05/Jul/21 10:49 PM | There are no comments yet on this issue. | 2021-07-05 21:09 | 16
PIMS-69324 | [EVT_FR&PADL] Help Text option don’t keep the change after reboot in BIOS. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 13448.038 | 2-Medium | 1. Boot to BIOS, turn off Help Text 2. Reboot to BIOS and check the option on or off. | Help Text option don’t keep the change after reboot in BIOS. Expected result: Help Text option should keep the change after reboot in BIOS. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.4 F/R: 2/2units, 4/4times. | There is no attachment uploaded | There are no comments yet on this issue. | 2021-07-05 21:09 | 16
PIMS-69303 | [EVT_FR&P ADL] Chicony Camera interface will turn green after change resolution several times. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | Input | 17775.016 | 2-Medium | 1、Open Camera APP and change resolution several times,Check if Camera interface will turn green. | Open Camera APP and change resolution several times, you will find Camera interface will turn green. Expected result: Camera interface should normal after change resolution several times. ** Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VNP on Luxvisions FW：1514 VP on Chicony FW：1611 Note: BIOS:0.0.4 OS:October 2021_22000.4 Intel Graphics Driver:30.0.100.9608 NV Graphics Driver:27.21.14.7076 Audio Driver:6.0.9159.1 Camera：Luxvisions FW：1514 Camera：Chicony FW：1611 F/R: 3/3units | Camera interface will turn green .mp4 3.69 MB 05/Jul/21 6:30 AM | There are no comments yet on this issue. | 2021-07-05 06:32 | 16
PIMS-69155 | [EVT_FR&P ADL] CPU frequence will drop and then keep 0.4GHz when charge AC or resume from S4/S5 on DC mode. | VERIFY | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | System Board | 14691.021 | 2-Medium | 1.Open "Task Manager" to view CPU "speed",check AC and DC mode state. | CPU frequence will drop and then keep 0.4GHz when charge AC or resume from S4/S5 on DC mode.(can recovery by DC mode restart) Details pls refer to attachment. Expected result: CPU frequence should change dynamically on AC/DC mode. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VP on AC mode VP on DC mode with S4/S5 VNP on DC mode with MS/WB Note: BIOS:0.0.4 F/R: 3/3units,12/12times. | CPU Frequence keep 0.4GHz.PNG 94 kB 04/Jul/21 8:08 PM | Kate Tsao(COMPAL) added a comment - 20/Jul/21 3:11 AM Found update EC 0.0.2 can fix issue, transfer PIMS to EC team for more update. Vic Dai(COMPAL) added a comment - 20/Jul/21 3:38 AM Related to Disable PECI PL3. Transfer to power for further update. Cage Yao(COMPAL) added a comment - 20/Jul/21 4:15 AM - edited Aligned with Dell PWR SA to disable PECI PsysPL3 and PL3, because that might impact CPU performance when dynamic PLx is active. Formal BIOS 0.0.6 has been implemented Bland yu(COMPAL) added a comment - 21/Jul/21 1:10 AM 2021/7/21,QAD_Bland,this issue VF on BIOS 0.0.6,OS:October_22000.4,F/R:0/2U,0/6T.So close the issue. | 2021-07-04 20:10 | 17
PIMS-69087 | [EVT_FRADL]Intel AX211 WiFi Driver can't be installed with EXE file and show message "The installation is forbidden by system policy". | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL | Driver | 13896 | 2-Medium | 1. Boot to OS and install Intel AX211 WiFi Driver; 2. Check whether it is installed successfully. | Intel AX211 WiFi Driver can't be installed by EXE and show message "The installation is forbidden by system policy". Please refer to attachment. Expected result: Intel AX211 WiFi Driver can install without any error. Issue isolation: VNP on FioranoP ADL VP on Fiorano ADL VP with EXE file VNP with INF file Note: BIOS:0.0.4 OS:October2021_22000.4 Intel AX211 WLAN driver:22.55.0.1 F/R: 2/2units, 5/5times | Intel AX211 WiFi Driver log.txt 17 kB 02/Jul/21 9:56 PM message.jpg 685 kB 02/Jul/21 9:56 PM | Elaine Lu(COMPAL) added a comment - 04/Jul/21 9:47 PM - edited [0705_SA_Elaine] Issue can found on XPS sku with AX211 driver package, this is expected behavior. Since AX211 package not bundle XPS SSID, we plan release solution driver package after WW29.5 from Dell and vendor feedback. Please install inf file first to test. Elaine Lu(COMPAL) added a comment - 20/Jul/21 9:47 PM [0721_SA_Elaine] Got vendor feedback, the solution driver release schedule postpone to release on W31.5 | 2021-07-02 22:00 | 19
PIMS-68726 | [EVT_FR&PADL] Run BIQ.ps1 EcTelemetry,It show Invalid Command. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 100842.053 | 2-Medium | 1. Run BIQ.ps1 EcTelemetry,It show Invalid Command.-->issue | Description: Run BIQ.ps1 EcTelemetry,It show Invalid Command. Expected result: [100842.053] BIOS – BIOS-IQ Telemetry (Dell-based BIOS, Gen11 and after) Step32. Ensure that this command functions Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.3 OS: October2021_21380.1001 BIQ_20200122 F/R:2/2units,2/2times. | BIQ_new.zip 39.57 MB 21/Jul/21 1:48 AM | There are no comments yet on this issue. | 2021-06-30 20:05 | 21
PIMS-68720 | [EVT_FR&PADL] The PTDT didn't exist in ACPI Table. | CLOSED | Resolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 100842.053 | 2-Medium | 1. Using RW Everything -> select ACPI Table 2. Scroll left to right through ACPI tables and look for the PTDT table.Find it didn't exist.-->issue | Description: Using RW Everything -> select ACPI Table, scroll left to right through ACPI tables and look for the PTDT table.Find it didn't exist. Expected result: [100842.053] BIOS – BIOS-IQ Telemetry (Dell-based BIOS, Gen11 and after) Step33. PTDT table exists in RWEverything tool. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.3 OS: October2021_21380.1001 RW:1.6.9 F/R:2/2units,2/2times. | 100842.053.png 10 kB 20/Jul/21 8:57 PM 100842.055.png 12 kB 20/Jul/21 8:57 PM | Lanny Lan(COMPAL) added a comment - 20/Jul/21 8:46 PM Test case update from 100842.053 to 100842.055 which add PHAT table in list. Current BIOS have PHAT table so this issue could be closed by test case update. Yoko Yin(COMPAL) added a comment - 20/Jul/21 9:11 PM 2021/07/21,Yoko_Yin,DQA,Test case update from 100842.053 to 100842.055 which add PHAT table in list. Current BIOS have PHAT table.So close this issue. | 2021-06-30 19:59 | 21
PIMS-67787 | [EVT_FRP ADL] MB can power on but LCD not light and its coolers are very hot. | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | System Board | 13435.041 | 2-Medium | 1.Power on SUT and check. | MB can power on but LCD not light and its coolers are very hot. MB PN/SN: 451ASD31L59#2 7108156100006 Expected result: No issue when power on SUT. Issue isolation: VP on FioranoP ADL Note: BIOS:0.0.0 F/R: 1/31units | There is no attachment uploaded | Bill Wu(COMPAL) added a comment - 03/Jul/21 7:55 PM - edited UT5 short cause system can’t power on. Tracking DVT1 SMT status. Ship to DQA PCBA all need to pass BFT. Update by Bill 07/04 | 2021-06-24 21:28 | 27
PIMS-67745 | [EVT_FR&PADL] The "error_log.txt" have fail item after run attributes script. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 13412.091 | 2-Medium | 1. Follow the TC-13412 steps to set up,then run command:python attributes.py. 2. Check the logs files show fail.-->issue | Description: Follow the TC-13412 steps to set up,then run command:python attributes.py. Check the error_log.txt . It show Fail: There are Platform Attributes that are not in the MasterList Attributes(possible multiple items): {'Legacy Manageability Interface Access': ['Enabled', 'ReadOnly', 'Disabled'], 'AmtCap': ['RestrictPrebootAccess']} Expected result: [13412.091] BIOS - (Automated-Partial) Attributes existence and setting (Dell-based BIOS X8 and after) Step4. "error_log.txt" file has nothing in it. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.2 OS: October2021_21380.1001 F/R:2/2units,2/2times. | AttributesRegistry_2.0.48.zip 120 kB 13/Jul/21 5:34 AM error_log.txt 0.2 kB 13/Jul/21 6:53 AM Log and tool.zip 120 kB 24/Jun/21 8:08 PM | Kate Tsao(COMPAL) added a comment - 27/Jun/21 12:43 AM Issue fail because new attributes from NUDD are not in AttributesRegistry_2.0.46. Kate Tsao(COMPAL) added a comment - 08/Jul/21 9:27 PM Update status: 1. 'Legacy Manageability Interface Access' fail because attribute name are not match with Masterlist. --> Cut in code change to FioranoAdl 0.0.5 BIOS. 2. 'AmtCap' fail because Masterlist lack 'RestrictPrebootAccess'. --> Wait DELL update Masterlist, tracking CPSE-5976 Kate Tsao(COMPAL) added a comment - 12/Jul/21 7:16 AM - edited Update status: 1. 'Legacy Manageability Interface Access' fail because attribute name are not match with Masterlist. --> Cut in code change to FioranoAdl 0.0.5 BIOS. 2. 'AmtCap' fail because Masterlist lack 'RestrictPrebootAccess'. --> Fixed by CBDCIT-745 Dell Bios Attributes Registry 2.0.48 Please help to verify with latest BIOS & tool. Yoko Yin(COMPAL) added a comment - 13/Jul/21 6:53 AM - edited 2021/07/13,Yoko_Yin.DQA,"error_log.txt" have new fail with BIOS:0.0.5 Attributes Registry 2.0.48.Please refer to the attachment.error_log.txt | 2021-06-24 20:13 | 27
PIMS-67744 | [EVT_FR&P ADL]External monitor can't light via Thunderbolt device connected | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | System Board | 51118 | 2-Medium | 1. Boot to OS,Conn external monitor to SUT via LaCie d2 Thunderbolt-3 External HDD/WD19TB/Gatkex Creek,external monitor not light. | Description: Boot to OS,Conn external monitor to SUT via LaCie d2 Thunderbolt-3 External HDD/WD19TB/Gatkex Creek,external monitor not light.1、Check device manager,DM can detect the monitor.2 Tjen rescan the DM,DM still can detect the monitor.3 WB the SUT,check the DM,DM still can detect the monitor. Expected result: The audio is set to the HDMI/DP digital audio output and it is working without any problems or issues. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VP on Thunderbolt HDD DP port VP on WD19TB VP on Gatkex Creek VP on TBT port IND on non-TBT port VNP on C-DP VNP on C-HDMI Note: BIOS:0.0.2 OS: October2021_21380.1001 F/R: 2/2units, 4/4times. PD FW: 64.31.64.31 Thunderbolt Driver:1.41.1134.0 Thunderbolt NVM:6.0 Intel Gfx:30.0.100.9563 WD19TB:A04 Gatkex Creek NVM:33 | 635566_ADL_M_P_TBTDisplayTunnelingIssue_SA_WW10_2021.pdf 119 kB 26/Jun/21 10:52 AM | Bill Wu(COMPAL) added a comment - 26/Jun/21 10:52 AM 1. Intel planned in future ADL QS to fix. 2. It will turn wait and verify on QS CPU. 06/26 update by Bill | 2021-06-24 20:10 | 27
PIMS-67563 | [EVT_FR&P ADL]MB can't power on after assembly and fan don't work. | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | System Board | 13435.041 | 2-Medium | 1.Power on SUT and check. | MB can't power on after assembly and fan don't work. 1.Can't power on and fan don't work,LED not show Amber when press power button. MB PN/SN: 451ASB31L60#1 7108730200021 451ASD31L60#5 7108156200010 451ASD31L59#1 7108156100031 451ASD31L59#5 7108156100016 2.Can't power on and fan don't work,LED shows Amber when press power button. MB PN/SN: 451ASB31L60#4 7108730200026 451ASB31L60#5 7108730200025 Expected result: No issue when power on SUT. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 F/R: 6/31units | There is no attachment uploaded | Bill Wu(COMPAL) added a comment - 06/Jul/21 9:02 PM After update BIOS all can boot , but need to use this PIMS tracking DVT1 factory process. update by Bill 07/07 | 2021-06-23 21:46 | 28
PIMS-67390 | [EVT_FR&P ADL]servicetag can't clear after run "serviceReset64W.exe clr" successfully | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | Embedded Solutions | 13564 | 2-Medium | 1. Boot to OS. 2. set "MfgMode64w +famm +osmm'->"serviceReset64W clr", show successful in OS,Boot to BIOS,check servicetag message. | Description: Boot to OS,set "MfgMode64w +famm +osmm'->"serviceReset64W clr", show "servicereset complete successfully" in OS,Boot to BIOS,found servicetag can't clear. Expected result: servicetag can clear Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.2 OS: October2021_21380.1001 F/R: 2/2units,6/6times. | There is no attachment uploaded | There are no comments yet on this issue. | 2021-06-22 21:31 | 29
PIMS-67166 | [EVT_FR&PADL] The SUT will show 2A3W and hang dell logo when WB/CB. | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | System Board | AD-hoc | 2-Medium | 1. The SUT will show 2A3W and hang dell logo when WB/CB .-->issue | Description: The SUT will show 2A3W and hang dell logo when WB/CB.Dirtyshutdow can recovery. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Hynix and Micron RAM VP Note: BIOS:0.0.2 OS: October2021_21380.1001 F/R:3/3units,3/12times. | There is no attachment uploaded | Bill Wu(COMPAL) added a comment - 26/Jun/21 9:36 AM 1. DDR5 SMBUS pull up resister is 1k ohm. 2. Intel feedback change to 4.7k ohm to try it and see if the failed symptom can be reproduced. 3. Rework 5 pcs can’t duplicate the issue. 4. RVP change the Pull up resistor from 1K to 4.7K in the Rev0.7 to Rev1.0 transition. 5. Rework all DQA PCBA RC71,RC73,RC56,RC54 from 1K to 4.7K and verify. 06/26 update by Bill Bill Wu(COMPAL) added a comment - 30/Jun/21 10:49 PM - edited Turn to verify. 07/01 update by EE Bill Yoko Yin(COMPAL) added a comment - 01/Jul/21 9:13 PM - edited 2021/07/02,Yoko_Yin,DQA,wait for the DVT1 unit to Verify this issue. | 2021-06-21 19:56 | 30
PIMS-67160 | [EVT_FR&PADL] Run UEFI SCT, Self Certification Test will get failure in the report. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 13483.013 | 2-Medium | 1. Create a bootable UEFI shell disk partition(FAT32) 2. Put the SCT tool to the partition 3. Boot and enter BIOS setup, ensure the FAT32 device/partition with the SCT is set first in the Boot Sequence 4. Reboot. Install the SCT using the binary file (example: cd "UEFI-SCT_Binary" -> "UEFI-SCT_Binary" -> "X64" -> run "InstallX64.efi" -> select your FAT32 partition). 5. CD to root then to "SCT" folder, run 'connect', and then run 'sct -a' 6. After complete generate a report -> 'sct -g Report.csv' 7. Open report file in Excel to check the result. | Description: After runnig UEFI Self Certification Test ,found some failure in the report. GenericTest\EFICompliantTest BootServicesTest\MiscBootServicesTest RuntimeServicesTest\VariableServicesTest DriverModelTest\AdapterInformationProtocolTest MediaAccessTest\SimpleFileSystemProtocolTest MediaAccessTest\BlockIOProtocolTest MediaAccessTest\NVMEPassThruTest MediaAccessTest\ATAPassThruProtocolTest NetworkSupportTest\SimpleNetworkProtocolTest HIITest\HIIConfigAccessProtocolTest HIITest\HIIConfigRoutingProtocolTest ConsoleSupportTest\SerialIOProtocolTest Expected result: [13483.013] BIOS - UEFI SCT, Self Certification Test Step6. There are no failures. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.2 OS: October2021_21380.1001 SCT:2.7B F/R:2/2units,2/2times. | Tool and report.zip 5.47 MB 22/Jun/21 2:17 AM | There are no comments yet on this issue. | 2021-06-21 19:47 | 30
PIMS-67024 | [EVT_FR&P ADL]Thunderbolt disable no function with Port1(Upper Port) | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 101145 | 2-Medium | 1. Boot to BIOS Setup,disable Thunderbolt Technology feature,save and exit. 2. Boot to OS,plug Thunderbolt devices to SUT,find SUT still can detect Thunderbolt device via Port1(Upper Port) | Description: Boot to BIOS Setup,disable Thunderbolt Technology feature,save and exit.Boot to OS,plug Thunderbolt devices to SUT,find SUT still can detect Thunderbolt device via Port1(Upper Port) Expected result: Thunderbolt devices can not be detect. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VP on Dell Thunderbolt SSD VP on Port1 VNP on Port2 Note: BIOS:0.0.2 OS: October2021_21380.1001 F/R: 2/2units, 6/6times. PD FW: 64.31.64.31 Thunderbolt Driver:1.41.1134.0 Thunderbolt NVM:6.0 | There is no attachment uploaded | There are no comments yet on this issue. | 2021-06-21 02:55 | 30
PIMS-66950 | [EVT_FR&P ADL] SUT shows "Error 207:Data verify mismatch found" when flash BIOS 0.0.2 at the first time. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 13435.041 | 2-Medium | 1.Flash BIOS and check whether shows Error. | SUT shows "Error 207:Data verify mismatch found" when flash BIOS 0.0.2 at the first time. Details pls refer to attachment. Expected result: No issue when flash BIOS. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.2 OS: October2021_21380.1001 F/R: 6/6units | BIOS 0.0.2 shows Error 207 when flash.png 749 kB 20/Jun/21 8:53 PM | There are no comments yet on this issue. | 2021-06-20 20:53 | 31
PIMS-66726 | [EVT_FR&PADL] The SUT can't keep on OROM interface when press hotkey CTRL+I . | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 13502.012 | 2-Medium | 1. Ensure 2 HDDs attached and set RAID On mode 2. Boot to OROM interface via press hotkey CTRL+I at post screen .Find the interface flash across and boot to OS. -->issue | Description: Ensure 2 HDDs attached and set RAID On mode.Boot to OROM interface via press hotkey CTRL+I at post screen.Find the interface flash across and boot to OS. Expected result: [13502.012] BIOS - Multiple function key press during boot Step1. The system should not hang or exhibit erratic behavior. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 OS: October2021_21380.1001 F/R:3/3units, 6/6times. | OROM interface flash across .MP4 577 kB 17/Jun/21 8:16 PM | There are no comments yet on this issue. | 2021-06-17 20:18 | 34
PIMS-66528 | [EVT_FR&P ADL] SUT shows Fail(not Found any Memory slot status: "Fail") after run 14701_Memory_SPD_Verification_Test.py in Powershell. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 14701.031 | 2-Medium | 1. According to 14701_Memory_SPD_Verification_Test_guideline.txt setup the test environment; 2. Run "python 14701_Memory_SPD_Verification_Test.py" command in Powershell, check result. | Running 14701_Memory_SPD_Verification_Test.py in Powershell, show "Not found any Memory slot status:Fail" and the fail result in result.json Memory information doesn't show in SPD and Memory page under CPU-Z. Details pls refer to attachment. Expected result: Run 14701_Memory_SPD_Verification_Test.py in Powershell, the result in result.json should show pass. Information of Installed Memory should show in SPD and Memory page under CPU-Z. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 OS: October2021_21380.1001 CPU-Z:1.96 F/R: 2/2units,4/4times. | cpu-z_1.96-en.zip 3.21 MB 12/Jul/21 6:14 AM Memory.PNG 186 kB 16/Jun/21 9:33 PM SPD_Slot1.PNG 169 kB 16/Jun/21 9:33 PM SPD_Slot2.PNG 170 kB 16/Jun/21 9:33 PM | Kate Tsao(COMPAL) added a comment - 13/Jul/21 11:19 AM - edited This should be common issue for ADL+DDR5 SKU, tracking PIMS-69667 and PIMS-69676. It might wait for the CPU-Z newer version to support AlderLake. Here is the note in CPU-Z website "Preliminary support of Intel Alder Lake and Z6xx platform". | 2021-06-16 21:33 | 35
PIMS-66324 | [EVT_FR&PADL] The POST didn't display a message when Decrease memory. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 14863.02 | 2-Medium | 1. Power off the SUT. Reduce the memory in the SUT 2. Power on the SUT. The POST didn't display a message when Decrease memory. -->issue | Description: Power off the SUT. Reduce the memory in the SUT. Power on the SUT. The POST didn't display a message when Decrease memory. Expected result: [14863.020] Memory - Memory Increase and Decrease Test Step7. The POST displays a message about the memory configuration being changed. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VNP on Increase Memory Note: BIOS:0.0.0 OS: October2021_21380.1001 F/R: 4/4units, 8/8times. | There is no attachment uploaded | There are no comments yet on this issue. | 2021-06-15 20:01 | 36
PIMS-66316 | [EVT_FR&PADL] The Installed RAM size in OS didn't change when Increase Memory. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 14863.02 | 2-Medium | 1. Increase the Memory. 2. Check "Installed Memory" from Control panel\ System\ About\ Installed RAM. The Installed RAM size didn't change. -->issue | Description: Increase the Memory. Check "Installed Memory" from Control panel\ System\ About\ Installed RAM. The Installed RAM size didn't change. Expected result: [14863.020] Memory - Memory Increase and Decrease Test Step 6, Ensure Installed RAM size is total install DIMM size. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 OS: October2021_21380.1001 F/R: 3/4units, 6/8times. | There is no attachment uploaded | There are no comments yet on this issue. | 2021-06-15 19:36 | 36
PIMS-66298 | [EVT_FR&PADL_RSV]SUT cannot boot up at 65c. | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL | Thermals | 108702 Temperature/Voltage Margin Test | 2-Medium | 1.Set up system to run AC power, with no battery installed. 2. Adjust voltage lines to +5% of nominal. Cycle power and reboot the system. Run a loop of system diagnostics and look for failures 3.When a failure does occur, see the note at the beginning of this section. Determine the passing limit for each voltage line individually. 4.collect and sort data | [Thermal 0625] Thermal has confirmed that there is no thermal event when it happened. Thermal just receive this PIMS for the after analysis. [Thermal 0628] Waiting for receiving the failed mainboards for the analysis. SUT cannot boot up at 65c. BIOS:0.0.0 F/R:2/2 | There is no attachment uploaded | There are no comments yet on this issue. | 2021-06-15 05:09 | 36
PIMS-66296 | [EVT_FR&PADL_RSV]SUT cannot boot up at -10c. | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL | Hardware | 108702 Temperature/Voltage Margin Test | 2-Medium | 1.Set up system to run AC power, with no battery installed. 2. Adjust voltage lines to +5% of nominal. Cycle power and reboot the system. Run a loop of system diagnostics and look for failures 3.When a failure does occur, see the note at the beginning of this section. Determine the passing limit for each voltage line individually. 4.collect and sort data | SUT cannot boot up at -10c. BIOS：0.0.0 F/R：2/2 | There is no attachment uploaded | Bill Wu(COMPAL) added a comment - 18/Jun/21 3:19 AM Align with Tributo PIMS-57658 and LKE ODYSSEY project , No design change for ES1 CPU , turn wait and tracking ES2/QS. 06/18 update by EE Bill | 2021-06-15 05:02 | 36
PIMS-66294 | [EVT_FR&PADL_RSV]SUT black screen with backlight when adjust +1.8v up to 1.89v (+5%). | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL | Hardware | REL1078 A14-Temperature/Voltage Margin Test | 2-Medium | 1.Set up system to run AC power, with no battery installed. 2. Adjust voltage lines to +5% of nominal. Cycle power and reboot the system. Run a loop of system diagnostics and look for failures 3.When a failure does occur, see the note at the beginning of this section. Determine the passing limit for each voltage line individually. 4.collect and sort data | SUT black screen with backlight when adjust +1.8v up to 1.89v (+5%). BIOS：0.0.0 F/R：2/2 | There is no attachment uploaded | Bill Wu(COMPAL) added a comment - 26/Jun/21 10:05 AM 1. System will show 2A3W after adjust high voltage. 2. Change DDR5 SUMBUS pull high resistor value from 1K to 4.7K ohm. 3. After rework , the system can power on and work normal after adjust high 10% voltage. 4. DDR5 SUMBUS pull high 1K cause system not stable. 5. Rework all DQA PCBA RC71,RC73,RC56,RC54 from 1K to 4.7K and verify. 06/26 update by EE Bill Jackie zhang(COMPAL) added a comment - 04/Jul/21 9:17 PM Regression test schedule: 7/7~7/13. Bill Wu(COMPAL) added a comment - 06/Jul/21 7:11 AM Remove DC1, pop RC156 +1.8V_PRIMP 348 → 3k (PR1603) +10%F/R : 0/10 can boot 1.980V 20k → 17k (PR1605) -10%F/R : 0/10 can boot 1.634V 07/06 update by EE Bill Alen Yang(COMPAL) added a comment - 06/Jul/21 9:52 PM Wait for next phase sample for validate. | 2021-06-15 04:57 | 36
PIMS-66280 | [EVT_FR&PADL_RSV]SUT black screen with backlight when adjust +3.3v up to 3.538v (+5%). | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | Hardware | 108702 Temperature/Voltage Margin Test | 2-Medium | 1.Set up system to run AC power, with no battery installed. 2. Adjust voltage lines to +5% of nominal. Cycle power and reboot the system. Run a loop of system diagnostics and look for failures 3.When a failure does occur, see the note at the beginning of this section. Determine the passing limit for each voltage line individually. 4.collect and sort data | SUT black screen with backlight when adjust +3.3v up to 3.538v (+5%). F/R:2/2 | There is no attachment uploaded | Bill Wu(COMPAL) added a comment - 26/Jun/21 10:06 AM 1. System will show 2A3W after adjust high voltage. 2. Change DDR5 SUMBUS pull high resistor value from 1K to 4.7K ohm. 3. After rework , the system can power on and work normal after adjust high 10% voltage. 4. DDR5 SUMBUS pull high 1K cause system not stable. 5. Rework all DQA PCBA RC71,RC73,RC56,RC54 from 1K to 4.7K and verify. 06/26 update by EE Bill Jackie zhang(COMPAL) added a comment - 04/Jul/21 9:20 PM Regression test schedule: 7/7~7/13. Bill Wu(COMPAL) added a comment - 06/Jul/21 7:09 AM Remove DC1, pop RC156 +3VALWP 69.8k → 86.6k (PR401) +10% F/R : 0/10 can boot 3.720V 69.8k → 51k (PR401) -10% F/R : 0/10 can boot 3.018V 07/06 update by EE Bill Alen Yang(COMPAL) added a comment - 06/Jul/21 9:54 PM Wait for next phase sample for validate. | 2021-06-15 05:24 | 36
PIMS-66188 | [EVT_FR&P ADL] CPU frequence keeps 40%-60%(can't reach 100%) when running CinebenchR20. | VERIFY | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | System Board | 14569.019 | 2-Medium | 1. Install CinebenchR20 and start it,click "File"->"Run all selected tests" to run. 2. During running process,open Task Manager "Performance" tab to view CPU frequence. | CPU frequence keeps low when running CinebenchR20.(40%-60%). Details pls refer to attachment. Expected result: CPU frequence can keep 100% and sometimes drop but then again keep 100% when running CinebenchR20. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 OS: October2021_21380.1001 CinebenchR20_v20.0.6.0 F/R: 2/2units,4/4times. | CPU frequence keeps low when running cinebench.mp4 3.08 MB 14/Jun/21 8:35 PM PIMS-66188_pass.mov.MOV 1.92 MB 21/Jul/21 2:53 AM | Leo Peng(COMPAL) added a comment - 21/Jul/21 2:57 AM Found update EC 0.0.2 can fix this issue. The test result of BIOS 0.0.5 is fail, but it can be pass after updating EC 0.0.2. PIMS-66188_pass.mov.MOV Test result: BIOS 0.0.5 : Fail BIOS 0.0.6 : Pass BIOS 0.0.5 + EC 0.0.2 : Pass Transfer PIMS to power team for more update. Cage Yao(COMPAL) added a comment - 21/Jul/21 3:07 AM Aligned with Dell PWR SA to disable PECI PsysPL3 and PL3, because that might impact CPU performance when dynamic PLx is active. Formal BIOS 0.0.6(EC 0.0.2) has been implemented. | 2021-06-14 20:36 | 37
PIMS-66169 | [EVT_FR&P ADL] STATE name show incorrect and SW/HW residency show blank when check SLP_S0 state with PHM. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 36554.021 | 2-Medium | 1. Install WDTF. Disconnect all USB devices. Connect Wi-Fi to a wireless Access PoinEnsuret. 2. Let SUT idle 10 minutes and ensure that CPU usage is stable. 3.Go to Collector Tab and select "ConnectedModernStandby_IdleScreenOff" under Preset Scenarios section. 4. Set the delayed start to 1 minute. Set the Scenario duration to 15 minutes and "start" data collection. 5.Wait until collection finishes, check SLP_S0 in PHM studysleep report. | Check system Modern Standby (SLP_S0) state with PHM, find STATE name show "Sleep", SW/HW residency show blank in PHM studysleep report.Details refer to attachment. Expected result: Check SLP_S0 state with PHM, STATE name should show "Modern Standby", SW % should be >= 90%, the Divergence between Software and Hardware residency should be <= 10%. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 OS: October2021_21380.1001 PowerHouse Mountain: v4.14.0 F/R: 2/2units,4/4times. | PHM SLP_S0.PNG 21 kB 14/Jun/21 5:26 AM | There are no comments yet on this issue. | 2021-06-14 05:29 | 37
PIMS-66164 | [EVT_FR&P ADL] SUT can't enter C10 state. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 14566.027 | 2-Medium | 1. Boot to BIOS Step and ensure C-States are enabled. 2. Boot to OS, install PHM (Powerhouse Mountain, v4.14.0) . 3. Start PHM, go to collector Tab. 4. Option section : Delayed start : 30sec , Scenario Duration:15min. 5. After completed, open the result traces. 6. Review report section , find can't enter into C10 state , only enter C3. | CPU can't enter into C10 state,only enter C3.Please refer to the picture. Expected result: CPU can enter into C10 state and able to reach spec. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 OS: October2021_21380.1001 F/R: 2/2units,4/4times. | can't enter C10 state.PNG 227 kB 14/Jun/21 5:33 AM | There are no comments yet on this issue. | 2021-06-14 04:52 | 37
PIMS-65909 | [EVT_FR&PADL] Some FW information can’t be detected in eDiag. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 100832.01 | 2-Medium | 1. Boot to eDiag, select ADVANCED TEST->SYSTEM INFO->FIRMWARE | Some FW information can’t be detected in eDiag (ex:Intel TbT Tetimer, System BIOS with BiosGuard, Main System Cypress Port Controller 0, Main System Cypress Port Controller 1, BiosConnect Core FV, BiosConnect Wireless FV, Microcode Update). Expected result: All FW information should be detected in eDiag. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 F/R: 2/2units, 4/4times. | FW information in eDiag.jpg 256 kB 10/Jun/21 8:14 PM | Kate Tsao(COMPAL) added a comment - 12/Jul/21 8:02 AM - edited Cut in code change in 0.0.4 BIOS for: ME/ISH/MCU FW version. | 2021-06-10 20:18 | 41
PIMS-65906 | [EVT_FR&PADL] Memory information location inverse and DIMM A lack BANK 0 with 2 RAM installed in eDiag. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 100832.01 | 2-Medium | 1. Boot to eDiag, check Memory information under ADVANCED TEST->SYSTEM INFO->MEMORY | Memory information location inverse and DIMM A lack BANK 0 with 2 RAM installed in eDiag. BANK 0 DIMM B show in DIMM A above. Expected result: Memory information should show BANK 0 DIMM A then show BANK 0 DIMM B. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VNP on 1 RAM installed Note: BIOS:0.0.0 F/R: 2/2units, 4/4times. | lack BANK 0.jpg 421 kB 10/Jun/21 8:07 PM | There are no comments yet on this issue. | 2021-06-10 20:18 | 41
PIMS-65905 | [EVT_FR&PADL] Memory information don’t show MFG information in eDiag. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 100832.01 | 2-Medium | 1. Boot to eDiag, check Memory information under ADVANCED TEST->SYSTEM INFO->MEMORY | Memory information don’t show MFG information in eDiag(ex: SK Hynix..) Expected result: Memory information should show MFG information in eDiag. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 F/R: 2/2units, 4/4times. | not show MFG information.jpg 421 kB 10/Jun/21 8:05 PM | Kate Tsao(COMPAL) added a comment - 12/Jul/21 5:17 AM Found there's no DDR5 offset define in Intel\AlderLake\ClientOneSiliconPkg\IpBlock\MemoryInit\Adl\LibraryPrivate\PeiMemoryInitLib\MemoryInit.c, created CPSE-6253 for tracking. | 2021-06-10 20:18 | 41
PIMS-65900 | [EVT_FR&PADL]Memory Channel Mode show incorrect in BIOS. | CLOSED | Resolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 13448.038 | 2-Medium | 1. Boot to BIOS, check Memory Channel Mode information under Overview->Memory | Memory Channel Mode show incorrect in BIOS. Condition 1: Memory Channel Mode show Dual with 1 RAM install. Condition 2: Memory Channel Mode show Quad with 2 same capacity RAM install. Condition 3: Memory Channel Mode show Mixed with 2 different capacity RAM install. Expected result: Memory Channel Mode should show Single/Dual with 1/2 Memory install. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 F/R: 2/2units, 4/4times. | Memory Channel Mode.jpg 184 kB 10/Jun/21 7:56 PM | Joseph Shih(COMPAL) added a comment - 18/Jul/21 11:15 PM Solution had cut into 0.0.6 BIOS. Please help to check. Thanks. Marcel Ma(COMPAL) added a comment - 21/Jul/21 1:42 AM Issue VNP on BIOS 0.0.6 . So close this issue. | 2021-06-10 20:17 | 41
PIMS-65896 | [EVT_FR&PADL] Memory Speed show 3600MHz with DDR5 4800MHz RAM install in BIOS/eDiag. | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | System Board | 13448.038 | 2-Medium | 1. Boot to BIOS, check Memory Speed information under Overview->Memory | Memory Speed show 3600MHz with DDR5 4800MHz RAM install in BIOS/eDiag. Expected result: Memory Speed should show 4800MHz with DDR5 4800MHz RAM install in BIOS/eDiag. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 F/R: 2/2units, 4/4times. | 635846_ES1_ADL_P_QXSG_QXSK_QXSJ_QXSH_DCL_WW09_2021.pdf 152 kB 17/Jun/21 8:39 AM memory msg shows in Task Manager.PNG 97 kB 04/Jul/21 9:28 PM Memory Speed.jpg 184 kB 10/Jun/21 7:51 PM | Bill Wu(COMPAL) added a comment - 17/Jun/21 8:44 AM EVT all use QXSG GPU and it's ES1 CPU. ES1 CPU DDR5Max Integrated Memory Controller Frequency limit on 3600. ES1 CPU DCL as attachment. 635846_ES1_ADL_P_QXSG_QXSK_QXSJ_QXSH_DCL_WW09_2021.pdf It will turn wait and verify on ES2 CPU. 06/17 update by Bill Bland yu(COMPAL) added a comment - 04/Jul/21 9:28 PM 2021/7/5,QAD_Bland,update status:Memory speed in OS->Task Manager->Performance tab also shows 3600MHz,details pls refer to attchment. | 2021-06-10 19:53 | 41
PIMS-65783 | [EVT_FR&PADL] TP/Mouse/TS will very lag in eDiag HEALTH table. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 100832.01 | 2-Medium | 1. Boot to eDiag, select ADVANCED TEST->SYSTEM INFO->HEALTH 2. Check Touchpad, Mouse and Touchscreen function | TP/Mouse/TS will very lag in eDiag HEALTH table. Touchpad and mouse curser can’t move. Touchscreen tap can’t select option. Expected result: TP/Mouse/TS should move smoothly in eDiag. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 F/R: 2/2units, 4/4times. | lag in eDIAG.MP4 31.27 MB 10/Jun/21 1:57 AM | There are no comments yet on this issue. | 2021-06-10 01:59 | 41
PIMS-65259 | [EVT_FR&PADL] The SUT will hang up when load FactoryDiagsManager.efi . | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 103848.01 | 2-Medium | 1. Boot the SUT into USB EFI Shell. 2. Run “load FactoryDiagsManager.efi.The SUT will hang up. --> Issue | Description: Boot the SUT into USB EFI Shell. Run “load FactoryDiagsManager.efi.The SUT will hang up. Expected result: [103848.010] eDiag v2.0: Enable factory to use eDiag v2.0 (Gen-12 (21Q1) or greater system) Step2, Run “load FactoryDiagsManager.efi.” Ensure you see a success message. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 OS: October2021_21380.1001 F/R: 4/4units, 8/8times. | FactoryDiagManager.efi 19 kB 10/Jun/21 8:50 PM hang up.jpg 305 kB 08/Jun/21 7:33 PM TestResult_LKEside.jpg 256 kB 08/Jun/21 4:32 AM UEFIShellFactoryDiagnostics_V1.1.zip 380 kB 08/Jun/21 4:32 AM | Joseph Shih(COMPAL) added a comment - 08/Jun/21 4:32 AM Hi Yoko Yin(COMPAL), Please help to upload your failed snapshot in PIMS and let us know which SKU you used for. In addition, could you help to help to double confirm SUT can reboot by press ctrl+alt+esc or not when issue present? Attached file is the test result in my side. Thank you. Yoko Yin(COMPAL) added a comment - 10/Jun/21 8:50 PM Hi Joseph Shih(COMPAL) The fail phenomenon has been upload.Press ctrl+alt+esc can't reboot. | 2021-06-07 01:41 | 44
PIMS-65083 | [EVT_FR&PADL] SUT can't detect monitor with HDMI/DP/VGA/Type-C dongle via TBT/non-TBT port. | WAIT | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | Hardware | 14562.013 | 2-Medium | 1、Connect monitor to SUT with HDMI/DP/VGA/Type-C dongle via TBT/non-TBT port. 2、Check if Monitor can be lighted and SUT candetect monitor in Device Manger. | Connect monitor to SUT with HDMI/DP/VGA/Type-C dongle via TBT/non-TBT port, you will find SUT can't detect monitor in Device Manger and it also show"Display connect mighted be limted". Rescan Device Manger and Restart SUT, SUT still can't detect monitor. Expected result: SUT can detect monitor and monitor can be lighted with HDMI/DP/VGA/Type-C dongle via TBT/non-TBT port. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VP on TBT/non-TBT port VP on HDMI/DP/VGA/Type-C Note: BIOS:0.0.0 OS:October2021_21380.1001 Intel Graphics Driver:30.0.100.9563 NV Graphics Driver:27.21.14.6253 Audio Driver:6.0.9159.1 F/R: 3/4units, 4/12times. | Display connect might be limited.jpg 57 kB 04/Jun/21 7:53 PM SUT can't detect monitor .mp4 9.07 MB 04/Jun/21 7:53 PM | Vic Dai(COMPAL) added a comment - 20/Jun/21 10:21 PM [2021/6/21 Vic]Related to DT66/DT68 Diode,Transfer to EE for further analyze Bill Wu(COMPAL) added a comment - 22/Jun/21 8:38 AM DT66/DT68 SMT well. JUSBC1 connector shift and JUSBC2 update BBR FW can workable. 06/22 update by Bill Fiona Yang(COMPAL) added a comment - 04/Jul/21 9:24 PM - edited 2021/7/5 Fiona_Yang VF this issue with BBR FW BIOS:0.0.4 OS:October 2021_22000.4 Intel Graphics Driver:30.0.100.9608 NV Graphics Driver:27.21.14.7076 Audio Driver:6.0.9159.1 Bill Wu(COMPAL) added a comment - 06/Jul/21 7:23 AM 1 pcs DT66/DT68 components miss. 2. BBR FW no update. Turn to wait tracking DVT1 SMT status. update by Bill 07/06 Bill Wu(COMPAL) added a comment - 06/Jul/21 7:24 AM 1 pcs DT66/DT68 components miss. 2. BBR FW no update. Turn to wait tracking DVT1 SMT status. update by Bill 07/06 | 2021-06-04 19:57 | 47
PIMS-65082 | [EVT_FR&PADL] SUT can't reboot to eDiag (trigger memory test) after run Notmyfault.exe. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 103771.012 | 2-Medium | 1. Run “Notmyfault.exe “ with administrative rights 2. Select Crash Tab and select High IRQL fault (Kernal Mode) 3. After SUT show BSOD, and boot to OS directly not occur eDiag.--> Issue | Description: In the OS, place Notmyfault.exe in the root directory of the USB key. Run “Notmyfault.exe“ with administrative rights, after SUT show BSOD, and boot to OS directly not occur eDiag.(FR:100%) Expected result: [103771.012] eDiag v2.0: The PCR-8099 - BSOD Triggered Memory Test Run Notmyfault.exe,system boot to eDiag after bluescreens. After reboot, system should be triggered memory test. Test #1: On a first boot, upon seeing the message, press "Yes" to let the eDiag run the advanced Memory Diagnostic test to heal the memory errors. Test #2: On a boot, upon seeing the message, press NO and ensure that the system boots to Windows OS successfully. Test #3: On a boot, upon seeing the message, do not press any key on the keyboard of the system under test and wait for 10-30 second for the short memory test to start. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.0 OS: October2021_21380.1001 ED.2.2.0 Notmyfault:4.1.0.0 F/R: 4/4units, 8/8times. | notmyfault64.exe 259 kB 08/Jun/21 10:58 PM | Yoko Yin(COMPAL) added a comment - 08/Jun/21 11:02 PM The notmyfault64 tool please refer to the attachment.notmyfault64.exe Joseph Shih(COMPAL) added a comment - 29/Jun/21 5:02 AM - edited This issue may be blocked by eDiag show Fan error after disable MFG mode. If skip fan check from eDiag, this issue can get the positive result. Will check this issue after MB can connect thermal module. | 2021-06-04 19:56 | 47
PIMS-64717 | [EVT_FR&PADL_D] Device Manager show NV YB in software devices item. | VERIFY | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 14562.013 | 2-Medium | 1. Boot to OS,install NV driver successfully 2. Device Manager show "NVIDIA Platform Controllers and Framework " YB in software devices item.--> Issue | Description: Boot to OS,install NV driver successfully. Device Manager show "NVIDIA Platform Controllers and Framework " YB in software devices item. Expected result: [14562.013] ULV: Phase Acceptance Test Report Card for Notebooks Step 11, Check to make sure that the Windows “Device Manager” does not show any bangs. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL VP on GN20-P0 & GN20-P1& QN20-P3 Note: BIOS:0.0.0 OS: October2021_21380.1001 F/R: 3/3units, 6/6times. | NV YB.jpg 41 kB 02/Jun/21 10:49 PM | Andy Wong1(COMPAL) added a comment - 20/Jul/21 12:21 AM Hi Yoko Yin(COMPAL) , BIOS 0.0.6 has implemented Dynamic Boost 2.0 , it can fix "NVIDIA Platform Controllers and Framework " YB. Please help verify. Thanks. | 2021-06-02 22:54 | 49
PIMS-67394 | [EVT_FR&PADL]Wan Miniport not list in device manager after boot to OS. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | Operating System | 13627.013 | 3-Low | 1. Install latest WLAN driver. 2. Reboot to OS. 3. Check Network adapters in Device Manager. | Boot to OS, check Network Adapters in Device Manager, find no Wan Miniport list in it. Wan Miniports can be list after click the network icon. Expected result: Some WAN Miniports should list in Device Manager after boot to OS. Issue isolation: VP on FioranoP ADL VP on Fiorano ADL Note: BIOS:0.0.2 OS:October2021_21380.1001 Intel AX211 WLAN driver:22.55.0.1 F/R: 2/2units, 5/5times | not show WAN Miniport .jpg 262 kB 22/Jun/21 9:31 PM WAN Miniport .JPG 189 kB 22/Jun/21 9:31 PM | Elvis Lee(COMPAL) added a comment - 23/Jun/21 12:24 AM [0623_SA_Elvis] Issue is VP on FI_22000.1_hotfix_22000.2, the WAN miniport does not list at device manager. As MSFT Bug #502274, this issue is under checking by MSFT. Elvis Lee(COMPAL) added a comment - 30/Jun/21 4:12 AM - edited [0630_SA_Elvis] Issue is VP on 22000.4 and 22000.51 (Preview Build). Issue can recover by click Wi-Fi task bar. As MSFT Bug #502274, this issue is under checking by MSFT. Elvis Lee(COMPAL) added a comment - 08/Jul/21 1:21 AM [0708_SA_Elvis] As MSFT Bug #502274 status, the problem is still seen by 22000.51 OS and under checking by MSFT. Elvis Lee(COMPAL) added a comment - 19/Jul/21 4:42 AM [0719_SA_Elvis] Issue is VP on 22000.71. Issue is under tracking by MSFT as Bug #502274. | 2021-06-22 21:36 | 29
PIMS-64553 | [EVT_FR&PADL] There are two Windows Boot Manager options in Boot Sequence and UEFI Boot Devices. | ANALYZE | Unresolved | VENDOR ACCESS Level | FIORANO ADL , FIORANO P MLK2 | BIOS | 14562.013 | 3-Low | 1.Boot to F2 or F12. 2.The Boot Sequence and UEFI boot Devices have two Windows Boot Manager options. | The Boot Sequence and UEFI boot Devices have two Windows Boot Manager options. | There is no attachment uploaded | There are no comments yet on this issue. | 2021-06-02 00:06 | 49

## Overdue
PIMS | Title | Platform Found | Submitted Date | Time lag
PIMS-59363 | Win,21370,WOR2021UPG,FR&PTGL, File Explorer interface will flash garbage when change show/hide under View | FIORANO P MLK , FIORANO TGL | 2021-05-11 20:42 | 71
PIMS-59369 | Win,21364,WOR2021FI,FR&PTGL, File Explorer interface will flash garbage when change show/hide under View | FIORANO P MLK , FIORANO TGL | 2021-05-11 20:51 | 71
PIMS-58807 | Win,21364,WOR2021FI, FR&PTGL, The taskview will leave over on the desktop when right-click desktop but not selected. | FIORANO P MLK , FIORANO TGL | 2021-05-09 19:55 | 73
PIMS-58856 | Win,21364,WOR2021UPG,FRPTGL,Microsoft account cannot sign in Feedback Hub always. | FIORANO P MLK | 2021-05-09 21:17 | 73
PIMS-58667 | Win,21364,WOR2021FI,FR&PTGL, The local music and video cannot be played successfully after connecting the Bluetooth headset/speaker. | FIORANO P MLK , FIORANO TGL | 2021-05-07 22:56 | 75
PIMS-64423 | Win,21380,WOR2021UPG,FR&PTGL, The local music and video cannot be played successfully after connecting the Bluetooth headset/speaker. | FIORANO P MLK , FIORANO TGL | 2021-06-01 06:02 | 50
PIMS-61922 | Win,21364,WOR2021FI,FR&PTGL,PowerDVD show error code=0011 when paly BD disk with PowerDVD 20. | FIORANO P MLK , FIORANO TGL | 2021-05-20 01:39 | 62
PIMS-61635 | Win,21376,WOR2021FI, FR&PTGL, Swiping 3-fingers can't switch apps by TP Slide to left/right | FIORANO P MLK , FIORANO TGL | 2021-05-19 20:20 | 63
PIMS-63349 | Win,21380,WOR2021UPG,FR&PTGL, No response when launching Voice Recorder from Start menu | FIORANO P MLK , FIORANO TGL | 2021-05-25 20:12 | 57
PIMS-64235 | Win,21385,WOR2021UPG,FR&PTGL,can't open "Windows Security settings". | FIORANO P MLK , FIORANO TGL | 2021-05-31 20:54 | 51
PIMS-66518 | [EVT_FR&PADL_RSV]Hynix RAM damaged at 2 degrees environment temperature | FIORANO ADL | 2021-06-16 21:04 | 35
PIMS-65137 | [EVT_FR&PADL] SUT can't boot with Micron memory and LED show 2A3W. | FIORANO ADL , FIORANO P MLK2 | 2021-06-05 03:34 | 46
PIMS-64550 | [EVT_FR&PADL] TBT port can't light TBT monitor | FIORANO ADL , FIORANO P MLK2 | 2021-06-02 20:09 | 49
PIMS-66950 | [EVT_FR&P ADL] SUT shows "Error 207:Data verify mismatch found" when flash BIOS 0.0.2 at the first time. | FIORANO ADL , FIORANO P MLK2 | 2021-06-20 20:53 | 31
PIMS-66726 | [EVT_FR&PADL] The SUT can't keep on OROM interface when press hotkey CTRL+I . | FIORANO ADL , FIORANO P MLK2 | 2021-06-17 20:18 | 34
PIMS-66528 | [EVT_FR&P ADL] SUT shows Fail(not Found any Memory slot status: "Fail") after run 14701_Memory_SPD_Verification_Test.py in Powershell. | FIORANO ADL , FIORANO P MLK2 | 2021-06-16 21:33 | 35
PIMS-66324 | [EVT_FR&PADL] The POST didn't display a message when Decrease memory. | FIORANO ADL , FIORANO P MLK2 | 2021-06-15 20:01 | 36
PIMS-66316 | [EVT_FR&PADL] The Installed RAM size in OS didn't change when Increase Memory. | FIORANO ADL , FIORANO P MLK2 | 2021-06-15 19:36 | 36
PIMS-66298 | [EVT_FR&PADL_RSV]SUT cannot boot up at 65c. | FIORANO ADL | 2021-06-15 05:09 | 36
PIMS-66296 | [EVT_FR&PADL_RSV]SUT cannot boot up at -10c. | FIORANO ADL | 2021-06-15 05:02 | 36
PIMS-66294 | [EVT_FR&PADL_RSV]SUT black screen with backlight when adjust +1.8v up to 1.89v (+5%). | FIORANO ADL | 2021-06-15 04:57 | 36
PIMS-66280 | [EVT_FR&PADL_RSV]SUT black screen with backlight when adjust +3.3v up to 3.538v (+5%). | FIORANO ADL , FIORANO P MLK2 | 2021-06-15 05:24 | 36
PIMS-66188 | [EVT_FR&P ADL] CPU frequence keeps 40%-60%(can't reach 100%) when running CinebenchR20. | FIORANO ADL , FIORANO P MLK2 | 2021-06-14 20:36 | 37
PIMS-66169 | [EVT_FR&P ADL] STATE name show incorrect and SW/HW residency show blank when check SLP_S0 state with PHM. | FIORANO ADL , FIORANO P MLK2 | 2021-06-14 05:29 | 37
PIMS-66164 | [EVT_FR&P ADL] SUT can't enter C10 state. | FIORANO ADL , FIORANO P MLK2 | 2021-06-14 04:52 | 37
PIMS-65909 | [EVT_FR&PADL] Some FW information can’t be detected in eDiag. | FIORANO ADL , FIORANO P MLK2 | 2021-06-10 20:18 | 41
PIMS-65906 | [EVT_FR&PADL] Memory information location inverse and DIMM A lack BANK 0 with 2 RAM installed in eDiag. | FIORANO ADL , FIORANO P MLK2 | 2021-06-10 20:18 | 41
PIMS-65905 | [EVT_FR&PADL] Memory information don’t show MFG information in eDiag. | FIORANO ADL , FIORANO P MLK2 | 2021-06-10 20:18 | 41
PIMS-65900 | [EVT_FR&PADL]Memory Channel Mode show incorrect in BIOS. | FIORANO ADL , FIORANO P MLK2 | 2021-06-10 20:17 | 41
PIMS-65896 | [EVT_FR&PADL] Memory Speed show 3600MHz with DDR5 4800MHz RAM install in BIOS/eDiag. | FIORANO ADL , FIORANO P MLK2 | 2021-06-10 19:53 | 41
PIMS-65783 | [EVT_FR&PADL] TP/Mouse/TS will very lag in eDiag HEALTH table. | FIORANO ADL , FIORANO P MLK2 | 2021-06-10 01:59 | 41
PIMS-65259 | [EVT_FR&PADL] The SUT will hang up when load FactoryDiagsManager.efi . | FIORANO ADL , FIORANO P MLK2 | 2021-06-07 01:41 | 44
PIMS-65083 | [EVT_FR&PADL] SUT can't detect monitor with HDMI/DP/VGA/Type-C dongle via TBT/non-TBT port. | FIORANO ADL , FIORANO P MLK2 | 2021-06-04 19:57 | 47
PIMS-65082 | [EVT_FR&PADL] SUT can't reboot to eDiag (trigger memory test) after run Notmyfault.exe. | FIORANO ADL , FIORANO P MLK2 | 2021-06-04 19:56 | 47
PIMS-64717 | [EVT_FR&PADL_D] Device Manager show NV YB in software devices item. | FIORANO ADL , FIORANO P MLK2 | 2021-06-02 22:54 | 49
PIMS-64553 | [EVT_FR&PADL] There are two Windows Boot Manager options in Boot Sequence and UEFI Boot Devices. | FIORANO ADL , FIORANO P MLK2 | 2021-06-02 00:06 | 49